## RMMS modifications
S.No | Comments from Client | Database changes | Development changes | Both Data & Development
1 | Facilitate the RMMS App to record Monthly progress as well. | Need clarity | Need clarity
2 | Facilitate the RMMS App to enter the name of the data entering Officer. | New field is added in base table "rmmsInspDet" with the field name "Officer" with data type as text | UI field has to be added in the app and provision should be given to add the name of the officer
3 | Stop appearing default data in the system (RIS) in following 3 fields to the data entering Officer. (Patching potholes, Crack sealing and Edge correction) | Data is being fetched from rmmsitmfld table and sp for visual condition
4 | Amend quantity calculation for the following items;
a | Patching potholes | Item fields were modified by the client and these fields were updated,but the quantity calculations not working | Need to recheck if the quantity calculations are hardcoded and modify them as per the requirement.
b | Edge correction | Item fields were modified by the client and these fields were updated,but the quantity calculations not working | Need to recheck if the quantity calculations are hardcoded and modify them as per the requirement.
c | Painting Bridge and Culvert | Item fields were modified by the client and these fields were updated,but the quantity calculations not working | Need to recheck if the quantity calculations are hardcoded and modify them as per the requirement.
d | Marking of Pedestrian Crossing | Item fields were modified by the client and these fields were updated,but the quantity calculations not working | Need to recheck if the quantity calculations are hardcoded and modify them as per the requirement.
5 | Data Entering limitations for the defined fields (Times per year, Lane marking width, etc. As given in page 2 of 2 in Annex A) | Max frequency value will be predefined in the item fields table. | Provision should be given in the UI in such a way that when frequnecy is chosen for a particular item UI should display number of screens/tabs based on the maximum frequency value of that item and it should not allow to store the data more than the maximum frequency count | Consider BMS spans screen as example.
6 | Apply following to all Items (As given in page 2 of 2 in Annex A);
a | Facilitating to appear units for all parameters | Units of measurement will be updated for all the parameters from database | If needed they need to add from UI as well
b | Chainage should be in meters (not in kms) | Datatype will be changed from float to int to allow only values in meters. | Need to check if this has to be modified in code as well.
c | Units should be in simple letters | Units of measurement will be updated for all the parameters from database | If needed they need to add from UI as well
7 | Rename the filter drop down menu name as "Filtered data" currently it is named as "Network" |  | Developers need to change
8 | In the same filter menu section freeze the parameter "TotalNetwork" by default as there are no multiple values |  | No need to provide the tota network field for selection
9 | In the home screen of app when filter is applied show the survey id parameter also in the filtered by screen and hide filtered by Total network parameter in the same |  | Developers need to modify
10 | The text type dashboard displayed in the app is not filtered based on year.
11 | In the dashboard screen check for the possibility of hiding the data in the text type chart if there is no data for a particular year selected. |  | Developers need to validate the data and display the output based on the year.
12 | Control dashboard display values to zero decimals | Database changes will be done and the values will be rouded to nearest interger
13 | In charts check if possible to change colour of the bars shown for each maintenance type and other caption changes. | Need to check from db end | need to check from developers as well
14 | In the survey section of RMMS disable the sync to web option until there is atleast one record enterd and saved by the user. |  | Developers need to change
15 | Last downloaded value shoudd not be cleared even if the user logs out and logins again and latest downloaded date should be displayed. |  | Change the format of date displayed to DD-MM-YYYY
16 | Provide screen rotation option in the app in the tab and mobile version layouts |  | Developer need to modify.
17 | Performance improvement for the app (loading of app is taking time) |  | Developers need to verify.