## RMMS modifications
S.No | Comments from Client | Database changes | Development changes | Both Data & Development | Support Team comments | Dev team comments
1 | Facilitate the RMMS App to record Monthly progress as well. |  |  |  | Data is displayed in the web application but not in the mobile app, developers need to check and let us know
2 | Facilitate the RMMS App to enter the name of the data entering Officer. | New field is added in base table "rmmsInspDet" with the field name "Officer" with data type as text | UI field has to be added in the app and provision should be given to add the name of the officer |  | New fields have been added in the main table to save the data of officer name and ee division.
3 | Stop appearing default data in the system (RIS) in following 3 fields to the data entering Officer. (Patching potholes, Crack sealing and Edge correction) | Data is being fetched from rmmsitmfld table and sp for visual condition |  |  | Developers need to stop the display of default data from visual condition sp for rmms data.
4 | Amend quantity calculation for the following items;
a | Patching potholes | Item fields were modified by the client and these fields were updated,but the quantity calculations not working | Need to recheck if the quantity calculations are hardcoded and modify them as per the requirement. |  | These calculations have been amended in the database and the same has been reflected in QA database for developers usage.
b | Edge correction | Item fields were modified by the client and these fields were updated,but the quantity calculations not working | Need to recheck if the quantity calculations are hardcoded and modify them as per the requirement. |  | These calculations have been amended in the database and the same has been reflected in QA database for developers usage.
c | Painting Bridge and Culvert | Item fields were modified by the client and these fields were updated,but the quantity calculations not working | Need to recheck if the quantity calculations are hardcoded and modify them as per the requirement. |  | These calculations have been amended in the database and the same has been reflected in QA database for developers usage.
d | Marking of Pedestrian Crossing | Item fields were modified by the client and these fields were updated,but the quantity calculations not working | Need to recheck if the quantity calculations are hardcoded and modify them as per the requirement. |  | These calculations have been amended in the database and the same has been reflected in QA database for developers usage.
5 | Data Entering limitations for the defined fields (Times per year, Lane marking width, etc. As given in page 2 of 2 in Annex A) | Max frequency value will be predefined in the item fields table. | Provision should be given in the UI in such a way that when frequnecy is chosen for a particular item UI should display number of screens/tabs based on the maximum frequency value of that item and it should not allow to store the data more than the maximum frequency count | Consider BMS spans screen as example. | The data in the frequency field should have data entry validations. For this validation to work, I have used the data from rmmsitmflds data table from the column FldVal. The data entered in this field will be displayed by default when an item code is selected. But there is one more validation to be considered, i.e., if the data in the column IsFreeze is having 1 as value and the data in the FldVal column is having value then the frequency of that item should be freezed in the app and user should not be able to edit it. If the data in the IsFreeze column is null or empty then the validation should be in such a way that the value displayed from the FldVal field should be the maximum value a user can enter for that particular item code.
6 | Apply following to all Items (As given in page 2 of 2 in Annex A);
a | Facilitating to appear units for all parameters | Units of measurement will be updated for all the parameters from database | If needed they need to add from UI as well |  | Field captions have been updated in the table and the same is reflected in the app as well.
b | Chainage should be in meters (not in kms) | Datatype will be changed from float to int to allow only values in meters. | Need to check if this has to be modified in code as well. |  | This has to be modifed by developers team from the code.
c | Units should be in simple letters | Units of measurement will be updated for all the parameters from database | If needed they need to add from UI as well |  | Updated the same in the database.
7 | Rename the filter drop down menu name as "Filtered data" currently it is named as "Network" |  | Developers need to change
8 | In the same filter menu section freeze the parameter "TotalNetwork" by default as there are no multiple values |  | No need to provide the tota network field for selection
9 | In the home screen of app when filter is applied show the survey id parameter also in the filtered by screen and hide filtered by Total network parameter in the same |  | Developers need to modify
10 | The text type dashboard displayed in the app is not filtered based on year.
11 | In the dashboard screen check for the possibility of hiding the data in the text type chart if there is no data for a particular year selected. |  | Developers need to validate the data and display the output based on the year.
12 | Control dashboard display values to zero decimals | Database changes will be done and the values will be rouded to nearest interger
13 | In charts check if possible to change colour of the bars shown for each maintenance type and other caption changes. | Need to check from db end | need to check from developers as well |  | This has been modified from the chart views and the same is reflected in the app dashboards.
14 | In the survey section of RMMS disable the sync to web option until there is atleast one record enterd and saved by the user. |  | Developers need to change
15 | Last downloaded value shoudd not be cleared even if the user logs out and logins again and latest downloaded date should be displayed. |  | Change the format of date displayed to DD-MM-YYYY
16 | Provide screen rotation option in the app in the tab and mobile version layouts |  | Developer need to modify.
17 | Performance improvement for the app (loading of app is taking time) |  | Developers need to verify.