## Core System
Item | Description | Remarks | Status | Priority | QA Status
System Security | Solid system security must be implemented for the core system, all platforms, database and all sub-systems. It must provide for the registration and validation of users. Registered users must be assigned roles which roles should govern which sub-systems, tables, screens and reports they are authorised to use, in terms of updating, amending, deleting and enquiry only. | Available. However security is at sub system level not at table / report level | Done |  | Unable to test
System Security | Solid password management principles should be adhered to in line with the ICT Policy. This should also include, forcing a user to change passwords after a specific date or period. | Available | Done |  | fail
Standard Outputs (Reports) | are to be accessible via a Management information function, which when accessed will list by title all available reports. The user has the option to display outputs on the screen and/or direct to a printer or export to a file. The user must be able to maintain reporting variables such as selection, criteria, sort sequence, sub group total etc. which can be saved for each selection scenario. There are 4 basic types of reporting requirements. | Report are provided at each sub system level | Done |  | fail
Typical Standard reports | which is used for providing standard information in a predefined format. For example, print a road log of all roads in a province. | Report is provided in RLRS | Re-verify |  | Pass
Exceptional reports | which are automatically produced by the system whenever a certain condition is matched, as defined by the user. For example, print all bridge approved projects outstanding with a maintenance priority of one. | Report is provided in PMS | Re-verify |  | fail
Periodic reports | that are automatically produced whenever a defined user date range have been matched. For example, print all new road construction projects registered this month. Such report must be printed at the start of the day that the day / date matches. | To be discussed |  |  | Fail
Ad-hoc reports | that the user can select at any time. This also includes the report types as described above. The user should also be able to select on predefined criteria before printing the report such as, from and to date, summarised or detailed, specific region or total network. | Available at each sub system level | Re-verify |  | Fail
Integrated Spatial Functionality | When dealing with large geographic areas it is more effective to portray data visually. Each road section should be allocated a unique GIS key which couples with a spatially drawn line on the geographic information system. This will provide a spatial map where each road is uniquely referenced. The system must also cater for various thematic map themes allowing for the accurate depiction or road segment properties such as road condition, maintenance projects, traffic volumes etc. The system must be enhanced to incorporate different types of aerial photographs as this functionality would assist users in the orientation process when perusing the maps of the country | Map function is available | Re-verify |  | Fail
Central Data Repository | Single source of data supply ensures accuracy, consistency and integrity in systems and services that reference and consume this data. It further promotes the importance of the sharing data between different stakeholders. As such the entire RAMS should follow this principle of single source data with integration throughout the single logical database structure | Available. Centralised database for storing all RAMS data. | Done |  | Unable to test
On-line Enquiry | One of the primary functions of the RAMS is the transparent availability of data and information. These are four main types of on-line enquiries that should be catered for: Main key enquiries whereby a user inputs the road reference number (or road name). For this type of enquiry the user must be able to input the data from the menu screen. This implies that those data fields should be provided next to or on the appropriate screen as a lookup field | Available in each sub system | Re-verify |  | Unable to test
Browse facility | whereby the user can scan the key data fields of all the data in the database and be able to select the required record. The selected record is then displayed showing all details. | Available in each sub system | Re-verify |  | Unable to test
Search matching facility | (utilising a search engine) whereby the user can search on a single field or if more information is known, on a number of fields. In addition, the user may use a wild card – ‘*’, or a ‘sounds like’ facility, where only part of the information is known on a field. For example, a part of a field description. (The system should then produce a list of values in the database beginning with a specific character or characters). | Available in each sub system. but need some enhancements to allow wild card search | Re-verify |  | Fail
Spatial facility | whereby the user can view the entire map and select the required road. The system should then obtain any relevant information pertaining to the selected road with the information to be displayed showing all details | Available in Map function. | Re-verify |  | Pass
Data Management Module (DMM) | A key element in the effective management of comprehensive software and information management systems is configuration and data management. A system such as the integrated road asset management (RAMS) collects and processes vast amounts of data. Examples of such data are traffic data from counting stations and detailed mechanical measurement data on the road network such as roughness end deflection measurements which represents a data record for every 500mm. In addition to raw data, various photo, video and spatial data is collected. | Available. But need to check and enhance – Need to be discussed | Re-verify |  | Unable to test
Data Management Module (DMM) | Long term sustainability of the RAMS with proper configuration management will require special emphasis on an overarching Data Management Module (DMM). | Available. But need to check and enhance – Need to be discussed | Re-verify |  | Unable to test
Data Management Module (DMM) | The intention is for the DMM to be the central collection point of any bulk data such as surveys to enter the database. Metadata is considered information about data or information and this would be a key aspect within the DMM. | Available. But need to check and enhance – Need to be discussed | Re-verify |  | Not able to test
Data Management Module (DMM) | The recommended DMM Functionality should include | Available. But need to check and enhance – Need to be discussed | Re-verify |  | Not able to test
Data Management Module (DMM) | · Manual Data Specification Standards | Available. But need to check and enhance – Need to be discussed | Re-verify |  | Not able to test
Data Management Module (DMM) | · Automated Data Specification Standards | Available. But need to check and enhance – Need to be discussed | Re-verify |  | Not able to test
Data Management Module (DMM) | · Raw Data Control | Available. But need to check and enhance – Need to be discussed | Re-verify |  | Not able to test
Data Management Module (DMM) | · Submitted Data Control | Available. But need to check and enhance – Need to be discussed | Re-verify |  | Not able to test
Data Management Module (DMM) | · Data Preparation for use by sub-systems | Available. But need to check and enhance – Need to be discussed | Re-verify |  | Not able to test
System Backup (Disaster Recovery) | A user-friendly system backup procedure is required for ensuring continuous backing up of data each day. The system is to detect that if a back-up has not been done by change of date, it should automatically execute a back-up to a remote site or external hard disk drive specifically installed to hold missed backup data. Should the system be switched off accidentally, or due to mains electricity power loss, the system is to automatically run a data integrity procedure to remove partially updated records from the database. This must be included in the system start up procedure | This is an Administrative activity to be performed at Server. To be discussed. |  |  | Not able to test

## ADMIN
Page/Menu | Menu Item | Item Description | Remarks | Status | Priority | QA Status
Language Management |  | Manages the language related words/phrases which are used to show in the application |  | Re-verify |  | Fail
Org. Structure Management | Agencies | manages (view/add/redit/delete) the Agencies data |  | Done |  | Pass
Org. Structure Management | Departments | manages (view/add/redit/delete) the departments data based on the Agencies |  | Done |  | Pass
Org. Structure Management | Positions | manages (view/add/redit/delete) the positions data based on the department and agencies |  | Done |  | Fail
User Management |  | manages (view/add/redit/delete) the users details; their access levels; their permissions etc., |  | Re-verify |  | Fail
Map Configuration |  | manages (view/add/redit/delete) the URL's used for accessing the reslective layers defined in ArcGIS. |  | Done |  | Pass
Send Notifications |  | Admin user can send notifications to a particular or group of users |  | Done |  | Pass
View Logs |  | Admin can view the application level user specific logs |  | Done |  | Pass
Audit Details |  | Admin can view the audit details like when a row was added, modified etc., by which user | Add this new item | Pending |  | Unable to test

## RLRS
Page/Menu | Menu Item | Item Description | Remarks | Status | Priority
Network Management > Jurisdiction | Province | manages(view/add/edit/delete) the province master data |  | Done | Pass
Network Management > Jurisdiction | District | manages(view/add/edit/delete) the district master data |  | Done | Pass
Network Management > Jurisdiction | Sector | manages(view/add/edit/delete) the sector master data |  | Done | Pass
Network Management > Lookup Data | Survey year configuration | manages(view/add/edit/delete) the survey year data used to upload the surveyed data respectively |  | Done | Fail
Network Management > Lookup Data | Link Types | manages(view/add/edit/delete) the link types master data | add this new item; used to define links for round abouts; overlaps; increasing; decreasing; etc., | Pending | Not able to test
Network Management > Lookup Data | Road Class | manages(view/add/edit/delete) the road class master data | gives the information about paved, unpaved, mixed, earthern, etc., | Done | Pass
Network Management > Lookup Data | Road Category | manages(view/add/edit/delete) the road category master data | NR ; DR1 ; DR2 ; etc., | Done | Pass
Network Management > Lookup Data | LRP Types | manages(view/add/edit/delete) the LRP types master data |  | Done | Pass
Network Management > Lookup Data | Sector Level Roads | manages(view/add/edit/delete) the road chainage at sector level master data |  | Re-verify | Pass
Network Management > Network Data | Road Master | manages(view/add/edit/delete) the road network data surveyed |  | Re-verify | Fail
Network Management > Network Data | Link Master | manages(view/add/edit/delete) the link network data surveyed |  | Re-verify | Fail
Network Management > Network Data | LRP Master | manages(view/add/edit/delete) the LRP points data surveyed |  | Re-verify | Fail
Network Management > Network Data | GPS Master | manages(view/add/edit/delete) the GPS coordinates of the road network data surveyed |  | In-progress | Pass
Network Management > Network Data | Survey Videos | manages the videos of the roads surveyed |  | Re-verify | Fail
Network Management > Tools | Split Link | We can split an existing link based on any LRP point on that link |  | Re-verify | Unable to test
| Merge Link | We can merge 2 adjacent existing links as a new link |  | Re-verify | Unable to test
Lookup Data > Road Inventory | Road Types | Manages (view/add/edit/delete) the master data for road types used in survey for complete network |  | Re-verify | Fail
Lookup Data > Road Inventory | Pavement Types | Manages (view/add/edit/delete) the master data for pavement Types used in survey for complete network |  | Re-verify | Pass
Lookup Data > Road Inventory | Surface Types | Manages (view/add/edit/delete) the master data for surface Types used in survey for complete network |  | Re-verify | Pass
Lookup Data > Road Inventory | Drain Types | Manages (view/add/edit/delete) the master data for drain Types used in survey for complete network |  | Re-verify | Pass
Lookup Data > Road Inventory | Shoulder Types | Manages (view/add/edit/delete) the master data for shoulder Types used in survey for complete network |  | Re-verify | Pass
Lookup Data > Road Inventory | Shoulder Widths | Manages (view/add/edit/delete) the master data for shoulder widths used in survey for complete network |  | Re-verify | Pass
Lookup Data > Road Inventory | Carriageway Types | Manages (view/add/edit/delete) the master data for carriageway Types used in survey for complete network |  | Re-verify | Pass
Lookup Data > Road Inventory | Cross Section Types | Manages (view/add/edit/delete) the master data for cross section Types used in survey for complete network |  | Re-verify | Pass
Lookup Data > Road Inventory | Terrain Types | Manages (view/add/edit/delete) the master data for terrain Types used in survey for complete network |  | Re-verify | Pass
Lookup Data > Road Inventory | ROW | Manages (view/add/edit/delete) the master data for ROW used in survey for complete network |  | Re-verify | Pass
Lookup Data > Road Inventory | Road Assets - Point | Manages (view/add/edit/delete) the master data for point assets used in survey for complete network |  | Re-verify | Pass
Lookup Data > Road Inventory | Road Assets - Section | Manages (view/add/edit/delete) the master data for section assets used in survey for complete network |  | Re-verify | Pass
Lookup Data > Road Condition | Roughness - IRI | Manages (view/add/edit/delete) the master data for Roughness - IRI used in survey for complete network |  | Re-verify | Pass
Lookup Data > Road Condition | Cracking Severity | Manages (view/add/edit/delete) the master data for cracking severity used in survey for complete network |  | Re-verify | Pass
Lookup Data > Road Condition | Ravelling Severity | Manages (view/add/edit/delete) the master data for ravelling severity used in survey for complete network |  | Re-verify | Pass
Lookup Data > Road Condition | Potholes Severity | Manages (view/add/edit/delete) the master data for pothole severity used in survey for complete network |  | Re-verify | Pass
Lookup Data > Road Condition | Edgebreak Severity | Manages (view/add/edit/delete) the master data for edgebreak severity used in survey for complete network |  | Re-verify | Pass
Lookup Data > Road Condition | Bleeding Severity | Manages (view/add/edit/delete) the master data for bleeding severity used in survey for complete network |  | Re-verify | Pass
Lookup Data > Road Condition | Depression Severity | Manages (view/add/edit/delete) the master data for depression severity used in survey for complete network |  | Re-verify | Pass
Lookup Data > Road Condition | Shoving Severity | Manages (view/add/edit/delete) the master data for shoving severity used in survey for complete network |  | Re-verify | Pass
Lookup Data > Road Condition | Shoulder Severity | Manages (view/add/edit/delete) the master data for shoulder severity used in survey for complete network |  | Re-verify | Pass
Lookup Data > Road Condition | Drain Condition | Manages (view/add/edit/delete) the master data for drain condition severity used in survey for complete network |  | Re-verify | Pass
Lookup Data > Road Condition | Roughness - BI | Manages (view/add/edit/delete) the master data for Roughness - BI used in survey for unsealed network |  | Re-verify | Pass
Lookup Data > Road Condition | Potholes | Manages (view/add/edit/delete) the master data for Potholes used in survey for unsealed network |  | Re-verify | Pass
Lookup Data > Road Condition | Corrugations | Manages (view/add/edit/delete) the master data for Corrugations used in survey for unsealed network |  | Re-verify | Pass
Lookup Data > Road Condition | Gravel Thickness | Manages (view/add/edit/delete) the master data for Gravel Thickness used in survey for unsealed network |  | Re-verify | Pass
Lookup Data > Road Condition | Drainage Condition | Manages (view/add/edit/delete) the master data for Drain condition used in survey for unsealed network |  | Re-verify | Pass
Lookup Data > Road Condition | Erosion Gullies | Manages (view/add/edit/delete) the master data for erosion gullies used in survey for unsealed network |  | Re-verify | Pass
Lookup Data > Road Condition | Rutting Severity | Manages (view/add/edit/delete) the master data for rutting used in survey for unsealed network |  | Re-verify | Pass
Lookup Data > Road Pavement | Base Types | Manages (view/add/edit/delete) the master data for base types used in survey for complete network |  | Re-verify | Pass
Lookup Data > Road Pavement | Subbase Types | Manages (view/add/edit/delete) the master data for subbase types used in survey for complete network |  | Re-verify | Pass
Lookup Data > Road Pavement | Pavement Subgrade Types | Manages (view/add/edit/delete) the master data for pavement subgrade types used in survey for complete network |  | Re-verify | Pass
Import |  | Imports / allows to upload the surveyed data of all parameters of road either for complete or unsealed |  | Re-verify | Unable to test
Manage Data > Road Inventory | Pavement Width | Manages (view/add/edit/delete) the surveyed pavement width data for complete network |  | Re-verify | Fail
Manage Data > Road Inventory | Pavement Type | Manages (view/add/edit/delete) the surveyed pavement type data for complete network |  | Re-verify | Fail
Manage Data > Road Inventory | Surface Type | Manages (view/add/edit/delete) the surveyed surface type data for complete network |  | Re-verify | Fail
Manage Data > Road Inventory | Drain Type | Manages (view/add/edit/delete) the surveyed drain type data for complete network |  | Re-verify | Fail
Manage Data > Road Inventory | Shoulder Type | Manages (view/add/edit/delete) the surveyed shoulder type data for complete network |  | Re-verify | Fail
Manage Data > Road Inventory | Shoulder Width | Manages (view/add/edit/delete) the surveyed shoulder width data for complete network |  | Re-verify | Fail
Manage Data > Road Inventory | Carriageway | Manages (view/add/edit/delete) the surveyed carriageway data for complete network |  | Re-verify | Fail
Manage Data > Road Inventory | Cross Sections | Manages (view/add/edit/delete) the surveyed cross section data for complete network |  | Re-verify | Fail
Manage Data > Road Inventory | Terrain | Manages (view/add/edit/delete) the surveyed terrain data for complete network |  | Re-verify | Fail
Manage Data > Road Inventory | Geometry | Manages (view/add/edit/delete) the surveyed geometry data for complete network |  | Re-verify | Fail
Manage Data > Road Inventory | Road Assets - Point | Manages (view/add/edit/delete) the surveyed point assets data for complete network |  | Re-verify | Fail
Manage Data > Road Inventory | Road Assets - Section | Manages (view/add/edit/delete) the surveyed section assets data for complete network |  | Re-verify | Fail
Manage Data > Road Condition | Condition Paved | Manages (view/add/edit/delete) the surveyed road condition data for complete network |  | Re-verify | Fail
Manage Data > Road Condition | Roughness - IRI | Manages (view/add/edit/delete) the surveyed Roughness - IRI data for complete network |  | Re-verify | Fail
Manage Data > Road Condition | Condition Unpaved | Manages (view/add/edit/delete) the surveyed road condition data for unsealed network |  | Re-verify | Pass
Manage Data > Road Condition | Roughness - BI | Manages (view/add/edit/delete) the surveyed Roughness - BI data for unsealed network |  | Re-verify | Pass
Manage Data > Pavement Details | FWD Data | Manages (view/add/edit/delete) the surveyed FWD data for complete network |  | Re-verify | Fail
Manage Data > Pavement Details | Pavement Composition | Manages (view/add/edit/delete) the surveyed pavement composition data for complete network |  | Re-verify | Pass
Manage Data > Pavement Details | Pavement History | Manages (view/add/edit/delete) the surveyed pavement history data for complete network |  | Re-verify | Unable to test
Execute Process | Check Missing Data | Generates the missing data ouptut |  | Done | Unable to test
Execute Process | Data Aggregation | Generates the network level data for analysis |  | Done | Unable to test
Execute Process | Set GPS Coordinates | Generates the GPS data to prepare the trafic layer |  | Done | Unable to test
Reports | Processed Data > Missing Data | shows the missing data |  | Re-verify | Pass
Reports > Road Inventory | Pavement Summary | Shows the pavement type summary data for the paved network |  | Re-verify | Pass
Reports > Road Inventory | Road Type Summary | Shows the road type summary data for the paved network |  | Re-verify
Reports > Road Inventory | Surface Type Summary | Shows the Surface type summary data for the paved network |  | Re-verify
Reports > Road Condition | Average Roughness (IRI) | Shows the roughness (IRI) summary data for the paved network |  | Re-verify
Reports > Road Condition | Paved Condition Summary | Shows the road condition summary data for the paved network |  | Re-verify
Reports > Road Condition | Average Roughness (BI) | Shows the roughness (BI) summary data for the unsealed network |  | Re-verify
Reports > Road Condition | Unpaved Condition Summary | Shows the road coondition summary data for the unsealed network |  | Re-verify
Reports > Pavement Details | FWD Summary | Shows the road FWD summary data for the paved network |  | Re-verify
Reports > Pavement Details | Pavement Composition Summary | Shows the pavement composition summary data for the paved network |  | Re-verify
Reports > Pavement Details | Pavement History Summary | Shows the pavement history summary data for the paved network |  | Re-verify
|  | The system must be a geolocation referencing system that forms the core foundation of RAMS | Need to discuss about the process for this |  | Unable to test
|  | The road network could initially be defined by importing the latest GIS layer and attributes into the system | Importing GPS data and attribute data is provided not the shape files |  | Unable to test
|  | As the central data repository and spatial foundation, the system is responsible for providing fixed network data to other sub-systems and services (e.g. data collection and assessment). | Available | Done | Unable to test
|  | Each item of information is coupled to a specific position or portion of the road. | Possible in map view | Done | Unable to test
|  | Full import and export functionality will be required. | Available | Done | Unable to test
|  | Road Network Versioning should also be incorporated | Data level versioning is available. Layer level is Not implemented | Re-verify | Unable to test
|  | This implies that all classes of roads must be catered for in the design of the system and database. | Available | Done | Unable to test
|  | Even though the RTDA is only responsible for National and Class 1 roads, it must be able to include urban and lower classes rural roads (feeder roads), should the need arise for these to be incorporated into the system. Although the RTDA is not responsible for the maintenance of these roads, it is recommended that the RTDA should be the custodian of this data | Available | Done | Unable to test
|  | By incorporating this information in the official RLRS database, the RTDA could provide this data to all other government authorities as well as tourism organisations and the private sector | Available | Done | Unable to test
|  | Having one custodian for road location reference in the country would be beneficial to the country and would reduce data duplication and redundancy of information, ensure compatibility between authorities and most importantly also have a major cost saving | Admin User only has the access to this function | Done | Unable to test
|  | Although recommended that RTDA manages the RLRS, the responsibility for data collection on the lower classes rural roads (feeder roads) and urban roads must be determined during development of the URFDS. | Provision is given in system to import other lower class roads | Done | Unable to test
|  | Consideration should be given that the RLRS be enhanced to incorporate aerial photographs as this functionality would assist users in the orientation process when perusing maps of the country. | Need Internal discussion |  | Unable to test
|  | The RLRS should incorporate all components to maintain an accurate Asset Register and Inventory to assist with calculation of the Asset Value in the future Network Integration Module. | not in scope of phase 1 |  | Unable to test
|  | Rwanda adopted a basic road classification process. Provision must be made to allocate the Road Class as an attribute to each road segment to view and report information per sub-network. | Available | Done | Unable to test

## PMS
Page/Menu | Menu Item | Item Description | Remarks | Status | Priority
Execute Process |  | The purpose of the PMS Inventory module is to generate the PMS inventory from the RLRS when a new road network becomes active. The module checks for a new network from the RLRS and alerts the PMS manager of the existence of a new network. The PMS Manager must have the option to activate updating of the network and must perform certain tasks when the new network is accepted within the PMS. | No Alert mechanism. But allows user to add edit inventory and condition data | Pending
Manage Data |  | Need to capture the following parameters for paved roads 1. Surfacing : failures; patching; binder condition(dry/brittle); aggregate loss; bleeding/flushing; deformation/shoving 2. Structural : block cracks; longitudinal cracks; transverse cracks; crocodile cracks; pumping; rutting; undulations/settlement; patching; failures/potholes 3. Functional assessments : Roughness; skid resistance; surface drainage; shoulders (paved); edge effects 4. Deflection measurements 5. Macro Texture depth measurements 6. Rut depth measurements 7. Visual condition assessments | Available to add/edit condition data. May be we can modify the menu title matching to this requirement. E.g. Condition to be changed to Assessment module. Need to include provision for texture depth table | Pending
|  | The purpose of a Riding Quality (Road roughness) Management module is to assist the Roads Authority in the calibration and control of riding quality (road roughness) measurement devices and to process information for direct import into the PMS. Note: At least ten roughness calibration/verification sections must be established close to, to calibrate Class 3 (response-type) equipment and to verify Class 1 devices | Calibration of equipment should not be part of RAMS system. hence only import for Roughness data is provided | Done
Lookup Data |  | The purpose of the Maintenance Policy and Cost module is to maintain one set of standard remedial measures and the cost thereof | Lookup tables provided to storing intervention criteria and related unit rates | Done
|  | The Condition Description module calculates the current condition of pavement components for purposes of communication, identification of needs and prioritisation of remedial measures | Need to discuss
|  | The purpose of a Resurfacing module is to identify the need for resurfacing/renewal measures, to provisionally prioritise these needs and to determine the most appropriate resurfacing type per project and funding requirement at the network level. It should be noted that the outputs from this module must be verified with panel inspections | Need to discuss
The Pavement Structure module identifies pavement rehabilitation needs on a network level and prioritises these needs in a five-year programme for budgeting purposes and to schedule detailed rehabilitation investigations
The purpose of the Optimisation module is to optimise the road network condition with the available funding in case of budget constraints.
The purpose of the Project Selection module is to generate more accurate programmes for resurfacing and rehabilitation projects. Candidate projects for resurfacing and rehabilitation are identified and provisionally prioritised from network level information
These projects are then confirmed through panel inspections and, if necessary with more detailed investigations after which final priority lists for resurfacing and rehabilitation projects are compiled and entered into the work schedules.
Execute Process |  | HDM Conversion module converts and exports information from the RLRS, PMS, URMS and TMS in a compatible format for HDM4 analyses, which incorporates evaluation of different life-cycle strategies (Refer Appendix A). | Available. | Done
|  | The Pavement Data module is used to capture, store and display pavement data on all road sections and to update the information when rehabilitation and resurfacing have been done. The pavement data captured in this module are also used to calculate the remaining structural life and is exported to the HDM4 data tables for further analysis. | Need to discuss
The purpose of the Vehicle Operating Cost (VOC) module is to capture/adjust vehicle operating cost factors and to calculate the total estimated vehicle operating cost per road segment.
The purpose of the Deterioration Setup module is to capture / adjust parameters defining pavement deterioration and the benefits of remedial measures under specific situations. This information is used to select appropriate remedial measures, to calculate the remaining life for prioritisation as well as to determine the implications of different funding scenarios.
Reports |  | The Output module enables the user to easily view and produce outputs generated in the various modules of the URMS | available | Re-verify
Reports > Processed Data | Missing Data | show the missing data for the respective paved roads |  | Re-verify
Reports > Processed Data | Homogeneous Sections | shows the homogeneous sections prepared by the system which is used for further analysis in HDM4 for the paved network |  | Re-verify
Reports > Road Inventory | Pavement Summary | Shows the pavement type summary data for the paved network |  | Re-verify
Reports > Road Inventory | Road Type Summary | Shows the road type summary data for the paved network |  | Re-verify
Reports > Road Inventory | Surface Type Summary | Shows the Surface type summary data for the paved network |  | Re-verify
Reports > Road Condition | Average Roughness (IRI) | Shows the roughness (IRI) summary data for the paved network |  | Re-verify
Reports > Road Condition | Paved Condition Summary | Shows the road condition summary data for the paved network |  | Re-verify
Reports > Pavement Details | FWD Summary | Shows the road FWD summary data for the paved network |  | Re-verify
Reports > Pavement Details | Pavement Composition Summary | Shows the pavement composition summary data for the paved network |  | Re-verify
Reports > Pavement Details | Pavement History Summary | Shows the pavement history summary data for the paved network |  | Re-verify
Reports > HDM4 Details | Sections Summary | Shows the sections summary obtained from the HDM4 for the paved network |  | Re-verify
Reports > HDM4 Details | Work Programme Summary | Shows the work treatment summary obtained from the HDM4 for the paved network |  | Re-verify
Reports > HDM4 Details | Cost Summary | Shows the cost summary obtained from the HDM4 for the paved network |  | Re-verify
Execute Process > Network Data | Paved Roads | prepares the consolidated summary of the complete paved network data surveyed and uploaded into the system for HDM analysis |  | Done
Execute Process > HDM4 program paved | Prepare Sections | prepares the homogeneous sections based on the criteria defined which is used in HDM4 for further analysis for paved network |  | Done
Execute Process > HDM4 program paved | Edit Sections | user can edit the homogeneous sections based on the LRP points if any needed | this is defined for phase 2, so not yet done | Pending
Execute Process > HDM4 program paved | Prepare HDM4 Data | prepares the data in the tables required by HDM4 to import into it for paved network |  | Done
Execute Process > HDM4 program paved | Export HDM4 Data | generates the .mdb file which will be imported into the HDM4 for further analysis for paved network |  | Done
Execute Process > HDM4 program paved | Import Rundata from HDM4 | imports the rundata prepared by HDM4 into the system and further reports are generated based on this data for paved network |  | Done
Manage Data > Road Inventory | Pavement Width | Manages (view/add/edit/delete) the surveyed pavement width data for paved network |  | Re-verify
Manage Data > Road Inventory | Pavement Type | Manages (view/add/edit/delete) the surveyed pavement type data for paved network |  | Re-verify
Manage Data > Road Inventory | Surface Type | Manages (view/add/edit/delete) the surveyed surface type data for paved network |  | Re-verify
Manage Data > Road Inventory | Drain Type | Manages (view/add/edit/delete) the surveyed drain type data for paved network |  | Re-verify
Manage Data > Road Inventory | Shoulder Type | Manages (view/add/edit/delete) the surveyed shoulder type data for paved network |  | Re-verify
Manage Data > Road Inventory | Shoulder Width | Manages (view/add/edit/delete) the surveyed shoulder width data for paved network |  | Re-verify
Manage Data > Road Inventory | Carriageway | Manages (view/add/edit/delete) the surveyed carriageway data for paved network |  | Re-verify
Manage Data > Road Inventory | Cross Sections | Manages (view/add/edit/delete) the surveyed cross section data for paved network |  | Re-verify
Manage Data > Road Inventory | Terrain | Manages (view/add/edit/delete) the surveyed terrain data for paved network |  | Re-verify
Manage Data > Road Inventory | Geometry | Manages (view/add/edit/delete) the surveyed geometry data for paved network |  | Re-verify
Manage Data > Road Inventory | Road Assets - Point | Manages (view/add/edit/delete) the surveyed point assets data for paved network |  | Re-verify
Manage Data > Road Inventory | Road Assets - Section | Manages (view/add/edit/delete) the surveyed section assets data for paved network |  | Re-verify
Manage Data > Road Condition | Condition Paved | Manages (view/add/edit/delete) the surveyed road condition data for paved network |  | Re-verify
Manage Data > Road Condition | Roughness - IRI | Manages (view/add/edit/delete) the surveyed Roughness - IRI data for paved network |  | Re-verify
Manage Data > Pavement Details | FWD Data | Manages (view/add/edit/delete) the surveyed FWD data for paved network |  | Re-verify
Manage Data > Pavement Details | Pavement Composition | Manages (view/add/edit/delete) the surveyed pavement composition data for paved network |  | Re-verify
Manage Data > Pavement Details | Pavement History | Manages (view/add/edit/delete) the surveyed pavement history data for paved network |  | Re-verify
Lookup Data > Road Inventory | Road Types | Manages (view/add/edit/delete) the master data for road types used in survey for paved network |  | Re-verify
Lookup Data > Road Inventory | Pavement Types | Manages (view/add/edit/delete) the master data for pavement Types used in survey for paved network |  | Re-verify
Lookup Data > Road Inventory | Surface Types | Manages (view/add/edit/delete) the master data for surface Types used in survey for paved network |  | Re-verify
Lookup Data > Road Inventory | Drain Types | Manages (view/add/edit/delete) the master data for drain Types used in survey for paved network |  | Re-verify
Lookup Data > Road Inventory | Shoulder Types | Manages (view/add/edit/delete) the master data for shoulder Types used in survey for paved network |  | Re-verify
Lookup Data > Road Inventory | Shoulder Widths | Manages (view/add/edit/delete) the master data for shoulder widths used in survey for paved network |  | Re-verify
Lookup Data > Road Inventory | Carriageway Types | Manages (view/add/edit/delete) the master data for carriageway Types used in survey for paved network |  | Re-verify
Lookup Data > Road Inventory | Cross Section Types | Manages (view/add/edit/delete) the master data for cross section Types used in survey for paved network |  | Re-verify
Lookup Data > Road Inventory | Terrain Types | Manages (view/add/edit/delete) the master data for terrain Types used in survey for paved network |  | Re-verify
Lookup Data > Road Inventory | ROW | Manages (view/add/edit/delete) the master data for ROW used in survey for paved network |  | Re-verify
Lookup Data > Road Inventory | Road Assets - Point | Manages (view/add/edit/delete) the master data for point assets used in survey for paved network |  | Re-verify
Lookup Data > Road Inventory | Road Assets - Section | Manages (view/add/edit/delete) the master data for section assets used in survey for paved network |  | Re-verify
Lookup Data > Road Condition | Roughness - IRI | Manages (view/add/edit/delete) the master data for Roughness - IRI used in survey for paved network |  | Re-verify
Lookup Data > Road Condition | Cracking Severity | Manages (view/add/edit/delete) the master data for cracking severity used in survey for paved network |  | Re-verify
Lookup Data > Road Condition | Ravelling Severity | Manages (view/add/edit/delete) the master data for ravelling severity used in survey for paved network |  | Re-verify
Lookup Data > Road Condition | Potholes Severity | Manages (view/add/edit/delete) the master data for pothole severity used in survey for paved network |  | Re-verify
Lookup Data > Road Condition | Edgebreak Severity | Manages (view/add/edit/delete) the master data for edgebreak severity used in survey for paved network |  | Re-verify
Lookup Data > Road Condition | Bleeding Severity | Manages (view/add/edit/delete) the master data for bleeding severity used in survey for paved network |  | Re-verify
Lookup Data > Road Condition | Depression Severity | Manages (view/add/edit/delete) the master data for depression severity used in survey for paved network |  | Re-verify
Lookup Data > Road Condition | Shoving Severity | Manages (view/add/edit/delete) the master data for shoving severity used in survey for paved network |  | Re-verify
Lookup Data > Road Condition | Shoulder Severity | Manages (view/add/edit/delete) the master data for shoulder severity used in survey for paved network |  | Re-verify
Lookup Data > Road Condition | Drain Condition | Manages (view/add/edit/delete) the master data for drain condition severity used in survey for paved network |  | Re-verify
Lookup Data > Road Pavement | Base Types | Manages (view/add/edit/delete) the master data for base types used in survey for paved network |  | Re-verify
Lookup Data > Road Pavement | Subbase Types | Manages (view/add/edit/delete) the master data for subbase types used in survey for paved network |  | Re-verify
Lookup Data > Road Pavement | Pavement Subgrade Types | Manages (view/add/edit/delete) the master data for pavement subgrade types used in survey for paved network |  | Re-verify
Lookup Data > Unit Rates | widening Costs | Manages (view/add/edit/delete) the master data for widening costs used in survey for paved network |  | Re-verify
Lookup Data > Unit Rates | Work Treatment Costs | Manages (view/add/edit/delete) the master data for treatment costs used in survey for paved network |  | Re-verify
Lookup Data > HDM4 Details | HDM4 Factors | Manages (view/add/edit/delete) the master data for HDM4 factors like calibration, other parameters default values which will be used in HDM4 analysis for paved network |  | Re-verify
Lookup Data > HDM4 Details | Accident Class / Speed Flow | Manages (view/add/edit/delete) the master data for HDM4 factors accident class or speed flow default values which will be used in HDM4 analysis for paved network |  | Re-verify
Lookup Data > Sectioning Definition | Define Sectioning Criteria | Defines the sectioning criteria to be used for generating the homogeneous sections for paved network |  | Re-verify
Lookup Data > Multi Criteria Analysis | MCA List | Manages (view/add/edit/delete) the master data for defining the multi criteria analysis like political influence, population, NPV value, etc., to be used for each road for paved network |  | In-progress
Lookup Data > Multi Criteria Analysis | Priority | Manages (view/add/edit/delete) the master data for defining the percentage applied for each multi criteria parameter to be used for each road for paved network |  | In-progress
The sequence of activities in the pavement management process as shown in Figure 8 are: • Road location referencing and inventory information • Data collection, which includes traffic data, condition surveys and climate information • Condition description to communicate the network status, deterioration and reporting of performance indicators • Deterioration modelling to predict future performance with different life-cycle strategies • Selection of appropriate remedial measures • Prioritisation through network optimisation, funding requirements and impact analysis • Presentation and funding motivation • Final project prioritisation to match funding availability • Allocation of funds to selected projects and programs • Project planning and scheduling • Detailed investigation and design • Construction (maintenance, rehabilitation or upgrading) • Updating of the inventory and asset register It is recommended that: • HDM4 be implemented to assist with optimised strategic planning and tactical planning of upgrading and rehabilitation projects (High capital expenditures). The added benefit of HDM4 is that results could be compared with other countries, making use of HDM4 or RONET (simplified HDM4 application) • A dedicated PMS be developed or customised for RTDA, specifically to assist with tactical planning and work program development of periodic maintenance activities

## URMS
Page/Menu | Menu Item | Item Description | Remarks | Status | Priority | QA Status
Execute Process |  | URMS Inventory module generates the URMS inventory from the RLRS when a new road network becomes active. The module checks for a new network from the RLRS and alerts the URMS manager of the existence of a new network. The URMS Manager must have the option to activate updating of the network and must perform certain tasks when the new network is accepted within the URMS. | need to check for the mechanism for Alerts. | Pending |  | Unable to test
Manage Data |  | Need to capture the following parameters for unsealed roads 1. Wearing course / surface : Gradeability; gravel thickness ; salt road condition 2. Material Properties : Type; maximum size; grading classification; approx. PI 3. Sub-grade : exposed sub-grade; support strength 4. Functional : Accessibility; Riding quality (roughness); safety; surface drainage; side drainage; number of drifts 5. Summary : general condition; recommended measures; sand blanket appropriate | Available to add/edit condition data. May be we can modify the menu title matching to this requirement. E.g. Condition to be changed to Assessment module. | Pending |  | Unable to test
Lookup Data |  | Maintenance Policy and Cost module to maintain one set of standard remedial measures and the cost thereof | Lookup tables provided to storing intervention criteria and related unit rates in PMS / URMS module | Done |  | Unable to test
Execute Process |  | Condition Description module calculates the current condition of pavement components for purposes of communication, identification of needs and prioritisation of remedial measures | Need to discuss |  |  | Unable to test
Execute Process |  | Treatment selection module identifies the need for periodic maintenance measures, to provisionally prioritise these needs and to determine the most appropriate remedial action per project and funding requirement at the network level. It should be noted that the outputs from this module must be verified with panel inspections | Need to discuss |  |  | Unable to test
Execute Process |  | Upgrading module identifies the economic viability to upgrade to surfaced standards and prioritises these needs in a five-year programme for budgeting purposes, and recommends a schedule for detailed feasibility studies | Need to discuss |  |  | Unable to test
Execute Process |  | HDM Conversion module converts and exports information from the RLRS, PMS, URMS and TMS in a compatible format for HDM4 analyses, which incorporates evaluation of different life-cycle strategies (Refer Appendix A). | Available in PMS which can be moved to URMS. | Done |  | Unable to test
Execute Process |  | Pavement Data module is used to capture, store and display pavement data on all road sections and to update the information when periodic maintenance and upgrading have been done. The pavement data captured in this module are also exported to the HDM4 data tables for further analysis | HDM option available in PMS which can be moved to URMS | Done |  | Unable to test
Execute Process |  | Deterioration Setup module is to capture/adjust parameters defining unsealed road deterioration and the benefits of remedial measures under specific situations. This information is used to select appropriate remedial measures, to prioritise and to determine the implications of different funding scenarios | Need to discuss |  |  | Unable to test
Reports |  | The Output module enables the user to easily view and produce outputs generated in the various modules of the URMS | available | Re-verify |  | Unable to test
|  | Km Posts need to be installed on all roads for referencing and reporting purposes | not in scope | NA |  | Unable to test
Reports > Processed Data | Missing Data | show the missing data for the respective unsealed roads |  | Re-verify |  | pass
Reports > Processed Data | Homogeneous Sections | shows the homogeneous sections prepared by the system which is used for further analysis in HDM4 for the unsealed network |  | Re-verify |  | pass
Reports > Road Inventory | Pavement Summary | Shows the pavement type summary data for the unsealed network |  | Re-verify |  | pass
Reports > Road Inventory | Road Type Summary | Shows the road type summary data for the unsealed network |  | Re-verify |  | pass
Reports > Road Inventory | Surface Type Summary | Shows the Surface type summary data for the unsealed network |  | Re-verify |  | pass
Reports > Road Condition | Average Roughness (BI) | Shows the roughness (BI) summary data for the unsealed network |  | Re-verify |  | pass
Reports > Road Condition | Unpaved Condition Summary | Shows the road coondition summary data for the unsealed network |  | Re-verify |  | pass
Reports > Pavement Details | Pavement Composition Summary | Shows the pavement composition summary data for the unsealed network |  | Re-verify |  | pass
Reports > Pavement Details | Pavement History Summary | Shows the pavement history summary data for the unsealed network |  | Re-verify |  | pass
Reports > HDM4 Details | Sections Summary | Shows the sections summary obtained from the HDM4 for the unsealed network |  | Re-verify |  | pass
Reports > HDM4 Details | Work Programme Summary | Shows the work treatment summary obtained from the HDM4 for the unsealed network |  | Re-verify |  | pass
Reports > HDM4 Details | Cost Summary | Shows the cost summary obtained from the HDM4 for the unsealed network |  | Re-verify |  | pass
Execute Process > Network Data | Unpaved Roads | prepares the consolidated summary of the complete unsealed network data surveyed and uploaded into the system for HDM analysis |  | Done |  | unable to test
Execute Process > HDM4 program unpaved | Prepare Sections | prepares the homogeneous sections based on the criteria defined which is used in HDM4 for further analysis for unsealed network |  | Done |  | unable to test
Execute Process > HDM4 program unpaved | Prepare HDM4 Data | prepares the data in the tables required by HDM4 to import into it for unsealed network |  | Done |  | unable to test
Execute Process > HDM4 program unpaved | Export HDM4 Data | generates the .mdb file which will be imported into the HDM4 for further analysis for unsealed network |  | Done |  | unable to test
Execute Process > HDM4 program unpaved | Import Rundata from HDM4 | imports the rundata prepared by HDM4 into the system and further reports are generated based on this data for unsealed network |  | Done |  | unable to test
Manage Data > Road Inventory | Pavement Width | Manages (view/add/edit/delete) the surveyed pavement width data for unsealed network |  | Re-verify |  | fail
Manage Data > Road Inventory | Pavement Type | Manages (view/add/edit/delete) the surveyed pavement type data for unsealed network |  | Re-verify |  | pass
Manage Data > Road Inventory | Surface Type | Manages (view/add/edit/delete) the surveyed surface type data for unsealed network |  | Re-verify |  | pass
Manage Data > Road Inventory | Drain Type | Manages (view/add/edit/delete) the surveyed drain type data for unsealed network |  | Re-verify |  | pass
Manage Data > Road Inventory | Shoulder Type | Manages (view/add/edit/delete) the surveyed shoulder type data for unsealed network |  | Re-verify |  | fail
Manage Data > Road Inventory | Shoulder Width | Manages (view/add/edit/delete) the surveyed shoulder width data for unsealed network |  | Re-verify |  | pass
Manage Data > Road Inventory | Carriageway | Manages (view/add/edit/delete) the surveyed carriageway data for unsealed network |  | Re-verify |  | pass
Manage Data > Road Inventory | Cross Sections | Manages (view/add/edit/delete) the surveyed cross section data for unsealed network |  | Re-verify |  | pass
Manage Data > Road Inventory | Terrain | Manages (view/add/edit/delete) the surveyed terrain data for unsealed network |  | Re-verify |  | pass
Manage Data > Road Inventory | Geometry | Manages (view/add/edit/delete) the surveyed geometry data for unsealed network |  | Re-verify |  | pass
Manage Data > Road Inventory | Road Assets - Point | Manages (view/add/edit/delete) the surveyed point assets data for unsealed network |  | Re-verify |  | pass
Manage Data > Road Inventory | Road Assets - Section | Manages (view/add/edit/delete) the surveyed section assets data for unsealed network |  | Re-verify |  | pass
Manage Data > Road Condition | Condition Unpaved | Manages (view/add/edit/delete) the surveyed road condition data for unsealed network |  | Re-verify |  | fail
Manage Data > Road Condition | Roughness - BI | Manages (view/add/edit/delete) the surveyed Roughness - BI data for unsealed network |  | Re-verify |  | pass
Manage Data > Pavement Details | Pavement Composition | Manages (view/add/edit/delete) the surveyed pavement composition data for unsealed network |  | Re-verify |  | fail
Manage Data > Pavement Details | Pavement History | Manages (view/add/edit/delete) the surveyed pavement history data for unsealed network |  | Re-verify |  | pass
Lookup Data > Road Inventory | Cross Section Types | Manages (view/add/edit/delete) the master data for Cross Sections used in survey for unsealed network |  | Re-verify |  | pass
Lookup Data > Road Inventory | Carriageway Types | Manages (view/add/edit/delete) the master data for Carriageway used in survey for unsealed network |  | Re-verify |  | pass
Lookup Data > Road Inventory | Drain Types | Manages (view/add/edit/delete) the master data for Drain Types used in survey for unsealed network |  | Re-verify |  | pass
Lookup Data > Road Inventory | Pavement Types | Manages (view/add/edit/delete) the master data for Pavement Types used in survey for unsealed network |  | Re-verify |  | pass
Lookup Data > Road Inventory | Surface Types | Manages (view/add/edit/delete) the master data for surface Types used in survey for unsealed network |  | Re-verify |  | pass
Lookup Data > Road Condition | Roughness - BI | Manages (view/add/edit/delete) the master data for Roughness - BI used in survey for unsealed network |  | Re-verify |  | pass
Lookup Data > Road Condition | Potholes | Manages (view/add/edit/delete) the master data for Potholes used in survey for unsealed network |  | Re-verify |  | pass
Lookup Data > Road Condition | Corrugations | Manages (view/add/edit/delete) the master data for Corrugations used in survey for unsealed network |  | Re-verify |  | pass
Lookup Data > Road Condition | Gravel Thickness | Manages (view/add/edit/delete) the master data for Gravel Thickness used in survey for unsealed network |  | Re-verify |  | pass
Lookup Data > Road Condition | Drainage Condition | Manages (view/add/edit/delete) the master data for Drain condition used in survey for unsealed network |  | Re-verify |  | pass
Lookup Data > Road Condition | Erosion Gullies | Manages (view/add/edit/delete) the master data for erosion gullies used in survey for unsealed network |  | Re-verify |  | pass
Lookup Data > Road Condition | Rutting Severity | Manages (view/add/edit/delete) the master data for rutting used in survey for unsealed network |  | Re-verify |  | pass
Lookup Data > Road Pavement | Base Types | Manages (view/add/edit/delete) the master data for base types used in survey for unsealed network |  | Re-verify |  | pass
Lookup Data > Road Pavement | Subbase Types | Manages (view/add/edit/delete) the master data for subbase types used in survey for unsealed network |  | Re-verify |  | pass
Lookup Data > Unit Rates | widening Costs | Manages (view/add/edit/delete) the master data for widening costs used in survey for unsealed network |  | Re-verify |  | Fail
Lookup Data > Unit Rates | Work Treatment Costs | Manages (view/add/edit/delete) the master data for treatment costs used in survey for unsealed network |  | Re-verify |  | fail
Lookup Data > HDM4 Details | HDM4 Factors | Manages (view/add/edit/delete) the master data for HDM4 factors like calibration, other parameters default values which will be used in HDM4 analysis for unsealed network |  | Re-verify |  | fail
Lookup Data > HDM4 Details | Accident Class / Speed Flow | Manages (view/add/edit/delete) the master data for HDM4 factors accident class or speed flow default values which will be used in HDM4 analysis for unsealed network |  | Re-verify |  | fail
Lookup Data > Sectioning Definition | Define Sectioning Criteria | Defines the sectioning criteria to be used for generating the homogeneous sections for unsealed network |  | Re-verify |  | pass
Lookup Data > Multi Criteria Analysis | MCA List | Manages (view/add/edit/delete) the master data for defining the multi criteria analysis like political influence, population, NPV value, etc., to be used for each road for unsealed network |  | In-progress |  | Unable to test
Lookup Data > Multi Criteria Analysis | Priority | Manages (view/add/edit/delete) the master data for defining the percentage applied for each multi criteria parameter to be used for each road for unsealed network |  | In-progress |  | Unable to test
The Unsealed Road Management System (URMS) must be developed as part of the Integrated Road Asset Management System and serves the purpose of assisting the RTDA in strategic and tactical planning on the unsealed road network. Activities required to provide and to maintain a safe and economical unsealed road network could be categorized into: • Routine road maintenance in the form of blading • Scheduled or periodic maintenance to improve accessibility, safety and maintainability e.g. regravelling, forming, reshaping • Identifying and prioritising upgrading to surfaced standards and sealing of gravel roads to preserve materials and to reduce maintenance and user costs • Ancillary works which include drainage improvements, emergency works and other maintenance requirements within the road reserve e.g. vegetation control, road signs and fences Similar to the PMS, the URMS will comprise different modules to obtain assessment data, to analyse this data and to report priorities and to recommended work programs

## RRMS
Page/Menu | Menu Item | Item Description | Remarks | Status | Priority
Lookup data / Import | Establishment Types |  |  | Done
Lookup data / Import | Institution Types |  |  | Done
Lookup data / Import | Land Types |  |  | Done
Lookup data / Import | Property Types |  |  | Done
Lookup data / Import | Settlement Types |  |  | Done
Lookup data / Import | Utility Types |  |  | Done
Lookup data / Import | Property Status Types |  | add this new lookup table under Lookups menu | Pending
Manage Data / Import | Establishments |  |  | Done
Manage Data / Import | Landuse |  |  | Done
Manage Data / Import | Property Details |  | Need to assign lookup table to status column and update the UI, service and DB accordingly | Re-verify
Manage Data / Import | ROW |  |  | Done
Manage Data / Import | Utilities > electric Grids |  |  | Done
Manage Data / Import | Utilities > Water Pipes |  |  | Done
Manage Data / Import | Utilities > Telecommunication Cables |  |  | Done
Execute Process | Check Missing Data | Generates the missing data ouptut |  | Done
Execute Process | Data Aggregation | Generates the network level data for analysis |  | Done
Execute Process | Set GPS Coordinates | Generates the GPS data to prepare the trafic layer |  | Done
Reports | Processed Data > Missing Data |  |  | Re-verify
Reports | Establishments |  |  | Re-verify
Reports | Landuse |  |  | Re-verify
Reports | Property Details |  |  | Re-verify
Reports | ROW |  |  | Re-verify
Reports | Utilities > electric Grids |  |  | Re-verify
Reports | Utilities > Water Pipes |  |  | Re-verify
Reports | Utilities > Telecommunication Cables |  |  | Re-verify
|  | Changes to the status of proclamation (replocamation to higher/lower category or deproclamation) and expropriation are captured in this sub-system and the information from the Road Proclamation System imported into the RLRS. | Need to enhance UI and reports to include such status. (4.5.1 - 2.7.6)
|  | This sub-system keeps track of the status of proclamation and expropriation to the physical construction of the facility, which then defines the detail to be captured in the asset register. | Need to discuss. (4.5.1 - 2.7.6)

## TMS
Page/Menu | Menu Item | Item Description | Remarks | Status | Priority
Report > Axle Load | Vehicle Damage Factor (VDF) | Show the VDF road-wise for axle 1 - 7, in road-wise and district-wise formats | move this report under Axle Load sub menu | Re-verify
Report > Axle Load | Road Life | Show the Roadlife based on the VDF and axle load counts in road-wise format | move this report under Axle Load sub menu | Re-verify
Report > Axle Load | Overloading | Need to include Overloading Report using Axle load data | add this new report under Axle Load sub menu | Pending
Report > Axle Load | E80’s | total number of E80’s (equivalent 80kN axle loads) | need to discuss ; add this new report under Axle Load sub menu | Pending
Report > Traffic Counts | Importance of Road | Shows the traffic data in ascending order of the ADT/AADT in road-wise format | add this new report under ADT /AADT sub menu | Pending
Report > Traffic Counts | ADT By Station | Show the ADT/AADT by Station road-wise for all vehicles being considered in traffic counts, in road-wise and district-wise formats | move this report under ADT /AADT sub menu | Re-verify
Report > Traffic Counts | ADT Hourly Variation | Show the ADT/AADT Hourly Variation and Peak hour for all vehicles combined in traffic counts, in station-wise format | move this report under ADT /AADT sub menu | Re-verify
Report > Traffic Counts | ADT Distribution by Mode | Show the ADT/AADT by vehicle mode for all vehicles considered group-wise in traffic counts, in station-wise format | move this report under ADT /AADT sub menu | Re-verify
Report > Traffic Counts | Daily ADT Distribution | Show the ADT/AADT by Distribution in date-wise for all vehicles being considered in traffic counts, in station-wise format | move this report under ADT /AADT sub menu | Re-verify
Report > Traffic Counts | Average Daily Traffic (ADT) | Show the ADT/AADT road-wise for all vehicles being considered in traffic counts, in road-wise and district-wise formats | move this report under ADT /AADT sub menu | Re-verify
Report > Others | V/C Ratio | Shows the V/C ratio data in road-wise and district-wise formats | add this new report under Others sub menu | Pending
Report > Others | Traffic Growth Rate | Show the ADT/AADT by Station road-wise for all vehicles being considered in traffic counts, in road-wise and district-wise formats | move this report under Others sub menu | Re-verify
Report > Others | Traffic Projection | Show the ADT/AADT by Station road-wise for all vehicles being considered in traffic counts, in road-wise and district-wise formats | move this report under Others sub menu | Re-verify
Report > Others | blading frequencies | Estimate blading frequencies for gravel and earth roads | need to discuss ; add this new report under others sub menu | Pending
Report > Others | queuing | queuing (platooning) length following distance (time) | need to discuss ; add this new report under others sub menu | Pending
Report > Day-wise | Daily Traffic Counts | Show the ADT/AADT by Station road-wise for all vehicles being considered in traffic counts, in road-wise and district-wise formats | add this report under Daily Counts sub menu | Re-verify
Report > Day-wise | Direction wise Daily Counts | Show the ADT/AADT by Station road-wise for all vehicles being considered in traffic counts, in road-wise and district-wise formats | add this report under Daily Counts sub menu | Re-verify
Report > Processed Data | Missing Data | show the missing data for the respective stations traffic count data for any missing time period or date |  | Re-verify
Report > Processed Data | Direction-wise Data | shows the output data of the direction-wise and day-wise | to be added, should use logic for seasonal factor also | Pending
Report > Processed Data | Station-wise Data | shows the output data of the station-wise | to be added, should use logic for seasonal factor also | Pending
Report > Processed Data | Day-wise Data | shows the output data of the direction-wise and day-wise | to be added, should use logic for seasonal factor also | Pending
Report > Processed Data | Link-wise Data | shows the output data of the link-wise | to be added, should use logic for seasonal factor also | Pending
Report > Processed Data | ADT and AADT data | shows the output of the traffic counts data road/link-wise AADT and AADT | to be added, should use logic for seasonal factor also | Pending
Execute Process | Check Missing Data | Generates the missing data ouptut |  | Done
Execute Process | Data Aggregation | Generates the network level data for analysis |  | Done
Execute Process | Set GPS Coordinates | Generates the GPS data to prepare the trafic layer |  | Done
Execute Process | Prepare ADT day-wise | generates the day-wise ADT based on the traffic counts data | need to generate AADT based on seasonal factors. | Re-verify
Execute Process | Prepare Average ADT day-wise | generates the day-wise ADT ; AADT based on the traffic counts data | need to generate AADT based on seasonal factors. | Re-verify
Execute Process | Generate ADT Stationwise | generates the station-wise ADT ; AADT based on the traffic counts data | need to generate AADT based on seasonal factors. Also need to find 30th highesdt peak value | Re-verify
Execute Process | Generate Projection | generates the station-wise Projections based on the traffic counts data |  | Re-verify
Execute Process | Generate Growth Rate | generates the station-wise Growth Rate based on the traffic counts data |  | Re-verify
Execute Process | Generate VDF and Road Life | generates the road-wise VDF and Road life based on the traffic counts data |  | Re-verify
Execute Process | Generate Overloading | generates the overload information based on the axle load data | add this new process based on the Axle load data and excels provided by client | Pending
Execute Process | Generate Blading ; E80's and Queing | generates the overload information based on the axle load data | need to discuss | Pending
Execute Process | Stratification of road links |  | need to discuss | Pending
Manage Data / Import | Traffic Stations / Master | manages the list of traffic stations used |  | Done
Manage Data / Import | TVC - 7 day counts | manages the counts of the vehicles passing by a traffic station | used for homogeneous sectioning | Done
Manage Data / Import | TVC - 7 day counts | Provision should be made for incorporating: • Public transport • Heavy vehicle and freight transport along the main international corridors | need to discuss | Pending
Manage Data / Import | Traffic Distribution | manages the traffic data to be used on the links where there is no traffic station based on the nearby stations | used for homogeneous sectioning | Re-verify
Manage Data / Import | Axle Load Counts | manages the counts of the vehicles passing by a weigh bridge | used for VDF and road life calculations | Re-verify
Manage Data / Import | Axle Load Survey | manages the wheel weights of the heavy vehicles | used for VDF calculations | Re-verify
Lookup Data / Import | Vehicle Classificaion | manages the classification of all vehicles used on Rwanda roads | used for TVC and Axle load data | Done
Lookup Data / Import | Traffic Category by ADT | manages the traffic range category data | used in showing charts, prioritising of sections | Done
Lookup Data / Import | V/C Range | manages the number of vehicles load based on the road type | used in calculating V/C ratio | Pending
Lookup Data / Import | Seasonal Factors | manages the seasonal factor for the traffic | used in calculating AADT based on the ADT | Pending
Lookup Data / Import | Commodity Type | manages the commodity/material types loaded in the vehicles | required for VDF calculation | Re-verify
Lookup Data / Import | Axle configuration | manages the axle configuartion of various vehicles | required for VDF calculation | Re-verify
Lookup Data / Import | Vehicle Axle Type | manages the type of vehilces and its axle configuation | required for VDF calculation | Re-verify
Lookup Data / Import | Growth Rates | manages the history of the growth rates of the vehicles, if any. | required for growth rate and projection of the traffic | Pending
Lookup Data / Import | Vehicle Operating Cost (VOC) | manages the vehicle costing parameters values used for HDM4 | need to export to mdb so that it will be imported in HDM4 for analysis. • prioritise actions • optimise on actions • undertake sensible economic analysis | Pending
Lookup Data / Import | Legal Maximum Load | manages the legal maximum load data for axle load vehicles | required for VDF calculation | Re-verify
Lookup Data / Import | Tare Weight Values | manages the tare weight values data |  | Re-verify
Lookup Data / Import | Vehicle Registrations | manages the vehicle registrations data |  | Pending
Dashboard | KPI | Total number of Traffic Stations |  | Done
Dashboard | KPI | Which station is having highest peak hour |  | Pending
Dashboard | KPI | Stations count from axle load data |  | Pending
Dashboard | Map | Stations layer |  | Re-verify
Dashboard | Map | AADT layer |  | Re-verify
Dashboard | Map | Remaining Life of road layer |  | Pending
Dashboard | Chart | Stations count district wise |  | Re-verify
Dashboard | Chart | AADT value district wise |  | Re-verify

## BMS
Page/Menu | Item Description | Remarks | Status | Priority
Table layout | show the basic details of the bridge in table |  | Done
Table layout | grid showing double scroll. | when we scroll to the last column in the table it is showing 2 scrolls.
Table layout | icon click to open the actual BMS website | opens the website in another tab | Done
Table layout | icon click to open General inventory for the selected bridge | opens the general inventory details in a popup | Done
Popup | General inventory of the selected bridge in the popup |  | Done
Table layout | icon click to open detailed inventory for the selected bridge | opens the detailed inventory details in a popup | Done
Popup | Detailed inventory of the selected bridge in the popup |  | Done
Table layout | icon click to open condition details for the selected bridge | opens the condition details in a popup | Done
Popup | Condition details of the selected bridge in the popup |  | Done
Table layout | icon click to export the bridge details shown in the table in excel format | exports the bridge details shown in the table in excel format | Done
Table layout | icon click for refreshing the data in the table |  | Done
Table layout | When we click on refresh icon, the sort icon in the table is not changing, | it should be cleared | Done
Table layout | search textbox for searching the data in the table |  | Done
Table layout | There is a time lag in displaying the text entered in the search textbox. | Better to use this textbox as free and put filter, cancel icons to refresh the data based on the search text entered
Table layout | selected row is being cleared after closing the popup | the selected row should be shown as highlighted and the icons of inventory, detailed and condition to be enabled
Table layout | show footer of the table with number of rows count | converted the normal table layout to grid with inbuilt features, so removing search textbox, manual sort and filter feature | Done

## Login and Dashboard
S.No. | Page / Menu | Menu Item | Item Description | Remarks | Status
1 | Modules bar |  | Better to fix the position and size | If want to animate it, better bring it on top instead of distrubing the whole page design when we mouse over it
2 | Map accordion |  | reduce the height of the map accordion a bit so that we can show the chart accordion also | currently user not able to see there is charts also unless he scrolls down, so we can show the chart accordion, so that user will have an idea there is charts below
| login |  | Show loading symbol till the complete login page displays
|  |  | Show message if password gets expired | As of now it is not showing any message nor it is going to dashboard page