## General or Home
S.No. | Menu / Page | Item Description | Remarks | DEV | QA | STAGE
|  | Need to show the notification icon above the user icon for the respective user after logging in, based on the notification created from admin module | not yet implemented | New

## BMS
S.No. | Item Description | Remarks | DEV | QA | STAGE
1 | Loading of the bridges list in table | Loading symbol should show till the data is binded in the table | Open
2 | Refresh icon click | Should show loading symbol when we click on refresh icon | Open
3 | Export the table data |  | Close
4 | Show general info of the selected bridge in popup, when we click on general info icon |  | Close
5 | Show inventory details of the selected bridge in popup, when we click on inventory details icon | The data is loading every time we click on the inception details box, even for the same which is already showing data | Open
6 | Show condition details on the selected bridge in popup, when we click on condition details icon | The data is loading every time we click on the inception details box, even for the same which is already showing data | Open
7 | External BMS website link when we click on the icon |  | Close
8 | Sorting and Filtering in the table |  | Close

## ADMIN
S.No. | Menu / Page | Item Description | Remarks | DEV | QA | STAGE
1 | Dashboard > KPI | Show data in KPIs |  | Close
2 | Dashboard > KPI | Show KPI related detailed data in table, when we click on KPI | Not showing the selected KPI detailed data in table | Open
3 | Dashboard > Charts | Charts to be discussed if any | Not showing any charts here, to be discussed if any chart required | Open
4 | Dashboard > Maps | nothing to show in map in admin module |  | NA
5 | Language Management | Show full data in table | Data not loading when the page is loaded for the first time | Open
6 | Language Management | Show the data in table based on the filter selection |  | Close
7 | Language Management | Sub-type dropdown should fill based on the type selected | need to add this new feature | New
8 | Language Management | Clear the filter and show complete data in table, when click on clear filters icon |  | Close
9 | Language Management | Action icons order Import ; Add ; Edit ; Delete ; Export |  | Close
10 | Language Management | Show the add new language data screen when click on Add New icon |  | Close
11 | Language Management | show the data of the selected item in form layout when click on Edit icon |  | Close
12 | Language Management | Show red * mark for mandatory fields | Not showing the red * mark for the mandatory fields in add / edit screen | Open
13 | Language Management | Cancel the add/edit screen and go back to table layout when click on cancel button in add/edit screen |  | Close
14 | Language Management | Add / update the new entered data and go back to table screen and refresh the table when submit button is clicked |  | Close
15 | Language Management | Delete the selected item when clicked on delete icon |  | Close
16 | Language Management | Export the table data in excel (.csv) format | if possible, try to set the file name as the menu name | Close
17 | Language Management | Show the import screen when click on import icon |  | Close
18 | Language Management | upload file when click on upload new file radio, then file browser and upload button |  | Close
19 | Language Management | show the uploaded file in the file dropdown |  | Close
20 | Language Management | Show the respective sheets of the selected file | Not showing the sheets list based on the selected file | Open
21 | Language Management | Import the language data from the excel file and sheet selected |  | Open
22 | Language Management | Cancel the import screen and go back to table layout when click on cancel button in import screen |  | Close
23 | Language Management | Show the summary import in the table |  | Open
24 | Org.Structures > Agencies | Show the complete data in table when 1st time |  | Close
25 | Org.Structures > Agencies | Filtered data to be shown in table |  | Close
26 | Org.Structures > Agencies | Action icons order Import ; Add ; Edit ; Delete ; Export | 1. Order is different. 2. need confirmation if import is needed here | Open
27 | Org.Structures > Agencies | Show the add new agency data screen when click on Add New icon |  | Close
28 | Org.Structures > Agencies | show the data of the selected item in form layout when click on Edit icon |  | Close
29 | Org.Structures > Agencies | Show red * mark for mandatory fields | Not showing the red * mark for the mandatory fields in add / edit screen | Open
30 | Org.Structures > Agencies | Cancel the add/edit screen and go back to table layout when click on cancel button in add/edit screen |  | Close
31 | Org.Structures > Agencies | Add / update the new entered data and go back to table screen and refresh the table when submit button is clicked |  | Close
32 | Org.Structures > Agencies | Delete the selected item when clicked on delete icon |  | Close
33 | Org.Structures > Agencies | Export the table data in excel (.csv) format | if possible, try to set the file name as the menu name | Close
34 | Org.Structures > Agencies | Show the import screen when click on import icon |  | Close
35 | Org.Structures > Agencies | upload file when click on upload new file radio, then file browser and upload button |  | Close
36 | Org.Structures > Agencies | show the uploaded file in the file dropdown |  | Close
37 | Org.Structures > Agencies | Show the respective sheets of the selected file | Not showing the sheets list based on the selected file | Open
38 | Org.Structures > Agencies | Import the agency data from the excel file and sheet selected |  | Open
39 | Org.Structures > Agencies | Cancel the import screen and go back to table layout when click on cancel button in import screen |  | Close
40 | Org.Structures > Agencies | Show the summary import in the table |  | Open
41 | Org.Structures > Departments | Show the complete data in table when 1st time | table not loading first time | Open
42 | Org.Structures > Departments | Filtered data to be shown in table based on the agency selected or the text entered |  | Close
43 | Org.Structures > Departments | Action icons order Import ; Add ; Edit ; Delete ; Export | Need confirmation if import is needed here | Close
44 | Org.Structures > Departments | Show the add new department data screen when click on Add New icon |  | Close
45 | Org.Structures > Departments | show the data of the selected item in form layout when click on Edit icon |  | Close
46 | Org.Structures > Departments | Show red * mark for mandatory fields | Not showing the red * mark for the mandatory fields in add / edit screen | Open
47 | Org.Structures > Departments | Cancel the add/edit screen and go back to table layout when click on cancel button in add/edit screen |  | Close
48 | Org.Structures > Departments | Add / update the new entered data and go back to table screen and refresh the table when submit button is clicked | Validation failed, even if we selected agency it is showing "please select Agency" message. | Open
49 | Org.Structures > Departments | Delete the selected item when clicked on delete icon |  | Close
50 | Org.Structures > Departments | Export the table data in excel (.csv) format | if possible, try to set the file name as the menu name | Close
51 | Org.Structures > Departments | Show the import screen when click on import icon |  | Close
52 | Org.Structures > Departments | upload file when click on upload new file radio, then file browser and upload button |  | Close
53 | Org.Structures > Departments | show the uploaded file in the file dropdown |  | Close
54 | Org.Structures > Departments | Show the respective sheets of the selected file | Not showing the sheets list based on the selected file | Open
55 | Org.Structures > Departments | Import the department data from the excel file and sheet selected |  | Open
56 | Org.Structures > Departments | Cancel the import screen and go back to table layout when click on cancel button in import screen |  | Close
57 | Org.Structures > Departments | Show the summary import in the table |  | Open
58 | Org.Structures > Positions | Show the complete data in table when 1st time | table not loading first time | Open
59 | Org.Structures > Positions | Filtered data to be shown in table based on the agency selected or the text entered |  | Close
60 | Org.Structures > Positions | Action icons order Import ; Add ; Edit ; Delete ; Export | Need confirmation if import is needed here | Close
61 | Org.Structures > Positions | Show the add new position data screen when click on Add New icon |  | Close
62 | Org.Structures > Positions | show the data of the selected item in form layout when click on Edit icon |  | Close
63 | Org.Structures > Positions | Show red * mark for mandatory fields | Not showing the red * mark for the mandatory fields in add / edit screen | Open
64 | Org.Structures > Positions | Cancel the add/edit screen and go back to table layout when click on cancel button in add/edit screen |  | Close
65 | Org.Structures > Positions | Add / update the new entered data and go back to table screen and refresh the table when submit button is clicked | Validation failed, even if we selected department it is showing "please select Department" message. | Open
66 | Org.Structures > Positions | Delete the selected item when clicked on delete icon |  | Close
67 | Org.Structures > Positions | Export the table data in excel (.csv) format | if possible, try to set the file name as the menu name | Close
68 | Org.Structures > Positions | Show the import screen when click on import icon |  | Close
69 | Org.Structures > Positions | upload file when click on upload new file radio, then file browser and upload button |  | Close
70 | Org.Structures > Positions | show the uploaded file in the file dropdown |  | Close
71 | Org.Structures > Positions | Show the respective sheets of the selected file | Not showing the sheets list based on the selected file | Open
72 | Org.Structures > Positions | Import the positions data from the excel file and sheet selected |  | Open
73 | Org.Structures > Positions | Cancel the import screen and go back to table layout when click on cancel button in import screen |  | Close
74 | Org.Structures > Positions | Show the summary import in the table |  | Open
75 | User Management | Show the complete data in table when 1st time | table not loading first time | Open
76 | User Management | Filtered data to be shown in table based on the user status, department, designation selected or the text entered |  | Close
77 | User Management | Action icons order Add ; Edit ; Status; Delete ; Export |  | Close
78 | User Management | Show the add new user data screen when click on Add New icon | 1. Labels for user name and phone no. is not aligned properly. 2. need to change the UI a few things to show the buttons in the same screen without scroll. 3. Password Expiry is not validated in UI 4. Department dropdown to be shown before the Designation dropdown. Also make these fields mandatory (show red * mark and validate them). 5. based on the department selected designation should be re-filtered. | Open
79 | User Management | show the data of the selected item in form layout when click on Edit icon | 1. Jurisdiction values is not displayed in the dropdown 2. Showing message as "Row Inserted Successfully" instead of "Row Updated Successfully" | Open
80 | User Management | Show red * mark for mandatory fields | Not showing the red * mark for the mandatory fields in add / edit screen | Open
81 | User Management | Cancel the add/edit screen and go back to table layout when click on cancel button in add/edit screen |  | Close
82 | User Management | Add / update the new entered data and go back to table screen and refresh the table when submit button is clicked |  | Close
83 | User Management | Change the status of the user either active or inactive | change the tooltip for the icon, it is showing as "Delete…" instead of "Change Status" | Open
84 | User Management | Delete the selected item when clicked on delete icon | Change the status of the selected user which is deleted as "Suspended" instead of Inactive | New
85 | User Management | Export the table data in excel (.csv) format | if possible, try to set the file name as the menu name | Close
86 | Map Configuration | Show the complete data in table when 1st time | table not loading first time | Open
87 | Map Configuration | Filtered data to be shown in table based on the user status, department, designation selected or the text entered |  | Close
88 | Map Configuration | Action icons order Add ; Edit ; Delete ; Export |  | Close
89 | Map Configuration | Show the add new map configuration data screen when click on Add New icon | 1. Show validation message for Layer Type as "Please Select Layer Type" instead of "Please Select Layer". 2. Show validation message for Layer Group as "Please Select Layer Group" instead of "Please Select Group". | Open
90 | Map Configuration | show the data of the selected item in form layout when click on Edit icon | not able to select a row in the table since loading symbol is showing | Open
91 | Map Configuration | Show red * mark for mandatory fields |  | Close
92 | Map Configuration | Cancel the add/edit screen and go back to table layout when click on cancel button in add/edit screen | data showing in table but loading symbol showing so page is not accessible | Open
93 | Map Configuration | Add / update the new entered data and go back to table screen and refresh the table when submit button is clicked | data showing in table but loading symbol showing so page is not accessible | Open
94 | Map Configuration | Delete the selected item when clicked on delete icon | data showing in table but loading symbol showing so page is not accessible | Open
95 | Map Configuration | Export the table data in excel (.csv) format | 1. data showing in table but loading symbol showing so page is not accessible 2. if possible, try to set the file name as the menu name | Open
96 | Send Notifications | Show the complete data in table when 1st time | table not loading first time | Open
97 | Send Notifications | Filtered data to be shown in table based on the user name selected or the text entered |  | Close
98 | Send Notifications | Action icons order Add ; Edit ; Delete ; Export |  | Close
99 | Send Notifications | Show the add new map configuration data screen when click on Add New icon | Label for Message is not properly aligned. | Open
100 | Send Notifications | show the data of the selected item in form layout when click on Edit icon |  | Close
101 | Send Notifications | Show red * mark for mandatory fields |  | Close
102 | Send Notifications | Cancel the add/edit screen and go back to table layout when click on cancel button in add/edit screen |  | Close
103 | Send Notifications | Add / update the new entered data and go back to table screen and refresh the table when submit button is clicked | 1. Mail functionality is not working(maybe due to DEV) | Open
104 | Send Notifications | Delete the selected item when clicked on delete icon | Showing message "Row Deleted Successfully", but the table is not refreshed | Open
105 | Send Notifications | Export the table data in excel (.csv) format | if possible, try to set the file name as the menu name | Close
106 | View Logs | Show the filtered log data in table based on the user selected |  | Close
107 | View Logs | Show the log details in new tab / window when clicked on the table row |  | Close
108 | View Audit | Show the audit details in table based on the user, table selected or as per the text entered | this is new feature - UI, service CRUD and database related tasks to be defined | New
109 | View Audit | Export the table data in excel (.csv) format | if possible, try to set the file name as the menu name | New

## TMS
S.No. | Menu / Page | Item Description | Remarks | DEV | QA | STAGE
1 | Dashboard > KPI | Show data in KPIs |  | Close
2 | Dashboard > KPI | Show KPI related detailed data in table, when we click on KPI |  | Close
3 | Dashboard > Charts | Show default charts as below 1. Traffic Station counts district wise. 2. Total ADT category district wise. | 1. Charts are sometimes flickering, need to check | Open
4 | Dashboard > Charts | Filter the chart data based on the surey year, Province, District | Charts are sometimes flickering, need to check | Open
5 | Dashboard > Charts | Click reload button to reload charts | Charts are sometimes flickering, need to check | Open
6 | Dashboard > Charts | Clear the filters and show default chart when click on Reset button |  | Close
7 | Dashboard > Map | Should show the boundary layer by default | map not loading | Open
8 | Lookup Data > Station Types | Show full data in table |  | Close
9 | Lookup Data > Station Types | Show the data in table based on the filter selection |  | Close
10 | Lookup Data > Station Types | Clear the filter and show complete data in table, when click on clear filters icon |  | Close
11 | Lookup Data > Station Types | Action icons order Add ; Edit ; Delete ; Export |  | Close
12 | Lookup Data > Station Types | Show the add new station types data screen when click on Add New icon |  | Close
13 | Lookup Data > Station Types | show the data of the selected item in form layout when click on Edit icon |  | Close
14 | Lookup Data > Station Types | Show red * mark for mandatory fields | Align the buttons properly | Open
15 | Lookup Data > Station Types | Cancel the add/edit screen and go back to table layout when click on cancel button in add/edit screen |  | Close
16 | Lookup Data > Station Types | Add / update the new entered data and go back to table screen and refresh the table when submit button is clicked |  | Close
17 | Lookup Data > Station Types | Delete the selected item when clicked on delete icon |  | Close
18 | Lookup Data > Station Types | Export the table data in excel (.csv) format | if possible, try to set the file name as the menu name | Close
19 | Lookup Data > Traffic Categories | Show full data in table | the data to be showed as order by Code instead of Name | Open
20 | Lookup Data > Traffic Categories | Show the data in table based on the filter selection |  | Close
21 | Lookup Data > Traffic Categories | Clear the filter and show complete data in table, when click on clear filters icon |  | Close
22 | Lookup Data > Traffic Categories | Action icons order Add ; Edit ; Delete ; Export |  | Close
23 | Lookup Data > Traffic Categories | Show the add new traffic categories data screen when click on Add New icon |  | Close
24 | Lookup Data > Traffic Categories | show the data of the selected item in form layout when click on Edit icon |  | Close
25 | Lookup Data > Traffic Categories | Show red * mark for mandatory fields | 1. Align the buttons properly 2. validate minimum value to be less than maximum value | Open
26 | Lookup Data > Traffic Categories | Cancel the add/edit screen and go back to table layout when click on cancel button in add/edit screen |  | Close
27 | Lookup Data > Traffic Categories | Add / update the new entered data and go back to table screen and refresh the table when submit button is clicked |  | Close
28 | Lookup Data > Traffic Categories | Delete the selected item when clicked on delete icon |  | Close
29 | Lookup Data > Traffic Categories | Export the table data in excel (.csv) format | if possible, try to set the file name as the menu name | Close
30 | Lookup Data > Time Period | Show full data in table | Not showing the DaySegment and Sequence values in the table and also not displaying the header for DaySegment | Open
31 | Lookup Data > Time Period | Show the data in table based on the filter selection | Filter not working when entered text as 60 | Open
32 | Lookup Data > Time Period | Clear the filter and show complete data in table, when click on clear filters icon |  | Close
33 | Lookup Data > Time Period | Action icons order Add ; Edit ; Delete ; Export |  | Close
34 | Lookup Data > Time Period | Show the add new time period data screen when click on Add New icon | 1. daysegment and sequence fields are not shown in the add/edit screen., they are also to be made as mandatory (show red * mark) and validate them. 2. interval field is not validated. 3. time period format is not displayed in the message or textbox | Open
35 | Lookup Data > Time Period | show the data of the selected item in form layout when click on Edit icon |  | Close
36 | Lookup Data > Time Period | Show red * mark for mandatory fields |  | Close
37 | Lookup Data > Time Period | Cancel the add/edit screen and go back to table layout when click on cancel button in add/edit screen |  | Close
38 | Lookup Data > Time Period | Add / update the new entered data and go back to table screen and refresh the table when submit button is clicked | submit button when in edit getting error | Open
39 | Lookup Data > Time Period | Delete the selected item when clicked on delete icon |  | Close
40 | Lookup Data > Time Period | Export the table data in excel (.csv) format | if possible, try to set the file name as the menu name | Close
41 | Lookup Data > Vehicle Classification | Show full data in table | show the data order by PCU value | Open
42 | Lookup Data > Vehicle Classification | Show the data in table based on the filter selection |  | Close
43 | Lookup Data > Vehicle Classification | Clear the filter and show complete data in table, when click on clear filters icon |  | Close
44 | Lookup Data > Vehicle Classification | Action icons order Add ; Edit ; Delete ; Export |  | Close
45 | Lookup Data > Vehicle Classification | Show the add new time period data screen when click on Add New icon | PCU validation should be before the HDM4 value validation | Open
46 | Lookup Data > Vehicle Classification | show the data of the selected item in form layout when click on Edit icon |  | Close
47 | Lookup Data > Vehicle Classification | Show red * mark for mandatory fields |  | Close
48 | Lookup Data > Vehicle Classification | Cancel the add/edit screen and go back to table layout when click on cancel button in add/edit screen |  | Close
49 | Lookup Data > Vehicle Classification | Add / update the new entered data and go back to table screen and refresh the table when submit button is clicked |  | Close
50 | Lookup Data > Vehicle Classification | Delete the selected item when clicked on delete icon |  | Close
51 | Lookup Data > Vehicle Classification | Export the table data in excel (.csv) format | if possible, try to set the file name as the menu name | Close
52 | Lookup Data > Seasonal Factors | Show full data in table |  | Close
53 | Lookup Data > Seasonal Factors | Action icons order Add ; Edit ; Delete ; Export |  | Close
54 | Lookup Data > Seasonal Factors | Show the add new seasonal factor data screen when click on Add New icon |  | Close
55 | Lookup Data > Seasonal Factors | show the data of the selected item in form layout when click on Edit icon |  | Close
56 | Lookup Data > Seasonal Factors | Show red * mark for mandatory fields |  | Close
57 | Lookup Data > Seasonal Factors | Cancel the add/edit screen and go back to table layout when click on cancel button in add/edit screen |  | Close
58 | Lookup Data > Seasonal Factors | Add / update the new entered data and go back to table screen and refresh the table when submit button is clicked | duplicate data should be checked based on survey year, ie. Each survey year will have only 1 row | Open
59 | Lookup Data > Seasonal Factors | Delete the selected item when clicked on delete icon |  | Close
60 | Lookup Data > Seasonal Factors | Export the table data in excel (.csv) format | if possible, try to set the file name as the menu name | Close
61 | Lookup Data > Vehicle Capacity Range | Show full data in table | show the data order by minimum and maximum values | Open
62 | Lookup Data > Vehicle Capacity Range | Show the data in table based on the filter selection |  | Close
63 | Lookup Data > Vehicle Capacity Range | Clear the filter and show complete data in table, when click on clear filters icon |  | Close
64 | Lookup Data > Vehicle Capacity Range | Action icons order Add ; Edit ; Delete ; Export |  | Close
65 | Lookup Data > Vehicle Capacity Range | Show the add new time period data screen when click on Add New icon |  | Close
66 | Lookup Data > Vehicle Capacity Range | show the data of the selected item in form layout when click on Edit icon |  | Close
67 | Lookup Data > Vehicle Capacity Range | Show red * mark for mandatory fields |  | Close
68 | Lookup Data > Vehicle Capacity Range | Cancel the add/edit screen and go back to table layout when click on cancel button in add/edit screen |  | Close
69 | Lookup Data > Vehicle Capacity Range | Add / update the new entered data and go back to table screen and refresh the table when submit button is clicked | validation of minimum value should be less than maximum value to be done | Open
70 | Lookup Data > Vehicle Capacity Range | Delete the selected item when clicked on delete icon |  | Close
71 | Lookup Data > Vehicle Capacity Range | Export the table data in excel (.csv) format | if possible, try to set the file name as the menu name | Close
72 | Lookup Data > Legal Maximum Load | Show full data in table | show the data order by no of tyres value | Open
73 | Lookup Data > Legal Maximum Load | Show the data in table based on the filter selection | 1. need to check for what fields do we have to consider the search. 2. Ideally should search for all fields | Open
74 | Lookup Data > Legal Maximum Load | Clear the filter and show complete data in table, when click on clear filters icon |  | Close
75 | Lookup Data > Legal Maximum Load | Action icons order Add ; Edit ; Delete ; Export |  | Close
76 | Lookup Data > Legal Maximum Load | Show the add new time period data screen when click on Add New icon | 1. Align the buttons to right side similar to other pages. 2. Formula field label is not properly aligned. 3. Remarks field validation is not required | Open
77 | Lookup Data > Legal Maximum Load | show the data of the selected item in form layout when click on Edit icon |  | Close
78 | Lookup Data > Legal Maximum Load | Show red * mark for mandatory fields | remove red * mark for remarks field | Open
79 | Lookup Data > Legal Maximum Load | Cancel the add/edit screen and go back to table layout when click on cancel button in add/edit screen |  | Close
80 | Lookup Data > Legal Maximum Load | Add / update the new entered data and go back to table screen and refresh the table when submit button is clicked |  | Close
81 | Lookup Data > Legal Maximum Load | Delete the selected item when clicked on delete icon |  | Close
82 | Lookup Data > Legal Maximum Load | Export the table data in excel (.csv) format | if possible, try to set the file name as the menu name | Close
83 | Lookup Data > Axle configuration | Show full data in table | show the data order by Permissible Vehicle Load value | Open
84 | Lookup Data > Axle configuration | Show the data in table based on the filter selection |  | Close
85 | Lookup Data > Axle configuration | Clear the filter and show complete data in table, when click on clear filters icon |  | Close
86 | Lookup Data > Axle configuration | Action icons order Add ; Edit ; Delete ; Export |  | Close
87 | Lookup Data > Axle configuration | Show the add new axle configuration data screen when click on Add New icon | 1. tolerance value should be between 0 and 100 and allow decimals 2. Remarks field validation is not required | Open
88 | Lookup Data > Axle configuration | show the data of the selected item in form layout when click on Edit icon |  | Close
89 | Lookup Data > Axle configuration | Show red * mark for mandatory fields | remove red * mark for remarks field | Open
90 | Lookup Data > Axle configuration | Cancel the add/edit screen and go back to table layout when click on cancel button in add/edit screen |  | Close
91 | Lookup Data > Axle configuration | Add / update the new entered data and go back to table screen and refresh the table when submit button is clicked |  | Close
92 | Lookup Data > Axle configuration | Delete the selected item when clicked on delete icon |  | Close
93 | Lookup Data > Axle configuration | Export the table data in excel (.csv) format | if possible, try to set the file name as the menu name | Close
94 | Lookup Data > Commodity Type | Show full data in table |  | Close
95 | Lookup Data > Commodity Type | Show the data in table based on the filter selection |  | Close
96 | Lookup Data > Commodity Type | Clear the filter and show complete data in table, when click on clear filters icon |  | Close
97 | Lookup Data > Commodity Type | Action icons order Add ; Edit ; Delete ; Export |  | Close
98 | Lookup Data > Commodity Type | Show the add new axle configuration data screen when click on Add New icon |  | Close
99 | Lookup Data > Commodity Type | show the data of the selected item in form layout when click on Edit icon |  | Close
100 | Lookup Data > Commodity Type | Show red * mark for mandatory fields |  | Close
101 | Lookup Data > Commodity Type | Cancel the add/edit screen and go back to table layout when click on cancel button in add/edit screen |  | Close
102 | Lookup Data > Commodity Type | Add / update the new entered data and go back to table screen and refresh the table when submit button is clicked |  | Close
103 | Lookup Data > Commodity Type | Delete the selected item when clicked on delete icon |  | Close
104 | Lookup Data > Commodity Type | Export the table data in excel (.csv) format | if possible, try to set the file name as the menu name | Close
105 | Lookup Data > Growth Rates | Show full data in table | Survey year field is not displayed in the table | Open
106 | Lookup Data > Growth Rates | Show the data in table based on the filter selection | need to add district filter dropdown, and filter the data based on the district selected | Open
107 | Lookup Data > Growth Rates | Clear the filter and show complete data in table, when click on clear filters icon |  | Close
108 | Lookup Data > Growth Rates | Action icons order Add ; Edit ; Delete ; Export |  | Close
109 | Lookup Data > Growth Rates | Show the add new axle configuration data screen when click on Add New icon | Remarks validation not required | Open
110 | Lookup Data > Growth Rates | show the data of the selected item in form layout when click on Edit icon | survey year value is not binding | Open
111 | Lookup Data > Growth Rates | Show red * mark for mandatory fields | remove red * mark for remarks field | Open
112 | Lookup Data > Growth Rates | Cancel the add/edit screen and go back to table layout when click on cancel button in add/edit screen |  | Close
113 | Lookup Data > Growth Rates | Add / update the new entered data and go back to table screen and refresh the table when submit button is clicked | duplicate data should be checked based on survey year and district, ie. Each survey year and district will have only 1 row | Open
114 | Lookup Data > Growth Rates | Delete the selected item when clicked on delete icon |  | Close
115 | Lookup Data > Growth Rates | Export the table data in excel (.csv) format | if possible, try to set the file name as the menu name | Close
116 | Import | Show import summary table based on the loged in user |  | Close
117 | Import | show the import screen when clicked on New Import button |  | Close
118 | Import | Show the below tables in table dropdown Axle configuration (L), Axlke Load Survey, Commodity Type (L), Growth Rates (L), Legal Maximum Load (L), Seasonal Factors (L), Station Types (L), Time Periods (L),, Traffic Categories(L), Traffic Distribution, Traffic Stations, Traffic Volume Counts, VEhicle Capacity Range (L), Vehicle Classification (L) | Remove Tare Weight Values (L) from the tables list and add Station Types (L) | Open
119 | Import | show / hide survey year dropdown based on the table selected, ie., if lookup table hide, if data table then show |  | Close
120 | Import | upload file when click on upload new file radio, then file browser and upload button |  | Close
121 | Import | show the uploaded file in the file dropdown |  | Close
122 | Import | Show the respective sheets of the selected file |  | Close
123 | Import | Columns Mismatch message will be shown if the respective excel-sheet columns not matching with the respective table columns |  | Close
124 | Import | once columns mismatch message is shown, the same should be updated in import table and then show the summary screen | as of now Validating status is being updated in the importdetails table, instead we update it as Failed and message to be shown as "Columns Mismatch" | New
125 | Import | If we get error as no data found in excel, then the same should be updated in import table and then show the summary screen | as of now Failed status is being updated in the importdetails table but no error message, instead we update it as Failed and message to be shown as "No Data Found in Excel" | New
126 | Import | Once the import is done either fail or success it should show summary screen |  | Close
127 | Import | When we click on the table row in summary table where Status is Failed and Error Count is more than 0 then should show error log screen |  | Close
128 | Import | export of the error log | need to give provision to export the error log in the error log screen | New
129 | Import | when click on back (<<) icon in error log screen show the table screen back |  | Close
130 | Manage Data > Traffic Stations | Show column headers of the respective table | columns not loading when the page is loaded for the first time | Open
131 | Manage Data > Traffic Stations | Show the data in table based on the filter selection |  | Close
132 | Manage Data > Traffic Stations | Traffic Stations dropdown should fill based on the road selected |  | Close
133 | Manage Data > Traffic Stations | Clear the filter and show complete data in table, when click on clear filters icon |  | Close
134 | Manage Data > Traffic Stations | Action icons order Add ; Edit ; Delete ; Gallery ; Export |  | Close
135 | Manage Data > Traffic Stations | Show the add new traffic station data screen when click on Add New icon |  | Close
136 | Manage Data > Traffic Stations | show the data of the selected item in form layout when click on Edit icon |  | Close
137 | Manage Data > Traffic Stations | Show red * mark for mandatory fields |  | Close
138 | Manage Data > Traffic Stations | Cancel the add/edit screen and go back to table layout when click on cancel button in add/edit screen |  | Close
139 | Manage Data > Traffic Stations | Add / update the new entered data and go back to table screen and refresh the table when submit button is clicked |  | Close
140 | Manage Data > Traffic Stations | Delete the selected item when clicked on delete icon |  | Close
141 | Manage Data > Traffic Stations | Show gallery screen either when traffic station dropdown is selected or any row is selected in the table | as of now it is validating only traffic station dropdown, need to take traffic station from the table if the row is selected | New
142 | Manage Data > Traffic Stations | Show the gallery screen with Images, Documents, Videos tabs with upload feature |  | Close
143 | Manage Data > Traffic Stations | upload the images, documents from the respective tabs |  | Close
144 | Manage Data > Traffic Stations | displays the uploaded images and documents in the respective tabs |  | Close
145 | Manage Data > Traffic Stations | Videos can be viewed, if any added from the backend at the respective path (Application folder/WebAPI/Gallery/Videos) | bhanu please update on this task as you have made few changes in this
146 | Manage Data > Traffic Stations | when click on back (<<) icon show the table screen back |  | Close
147 | Manage Data > Traffic Stations | Export the table data in excel (.csv) format | if possible, try to set the file name as the menu name | Close
148 | Manage Data > Traffic Volume Counts | Show column headers of the respective table | columns not loading when the page is loaded for the first time | Open
149 | Manage Data > Traffic Volume Counts | Show the data in table based on the filter selection | loading symbol not showing when data is binding | Open
150 | Manage Data > Traffic Volume Counts | Traffic Stations dropdown should fill based on the road selected |  | Close
151 | Manage Data > Traffic Volume Counts | Clear the filter and show complete data in table, when click on clear filters icon | loading symbol not showing when data is binding | Open
152 | Manage Data > Traffic Volume Counts | Action icons order Add ; Edit ; Delete ; Gallery ; Export |  | Close
153 | Manage Data > Traffic Volume Counts | Show the add new traffic volume count data screen when click on Add New icon |  | Close
154 | Manage Data > Traffic Volume Counts | show the data of the selected item in form layout when click on Edit icon | 1. Buttons not aligned properly | Open
155 | Manage Data > Traffic Volume Counts | Show red * mark for mandatory fields |  | Close
156 | Manage Data > Traffic Volume Counts | Cancel the add/edit screen and go back to table layout when click on cancel button in add/edit screen |  | Close
157 | Manage Data > Traffic Volume Counts | Add / update the new entered data and go back to table screen and refresh the table when submit button is clicked |  | Close
158 | Manage Data > Traffic Volume Counts | Delete the selected item when clicked on delete icon |  | Close
159 | Manage Data > Traffic Volume Counts | Show gallery screen either when traffic station dropdown is selected or any row is selected in the table | as of now it is validating only traffic station dropdown, need to take traffic station from the table if the row is selected | New
160 | Manage Data > Traffic Volume Counts | Show the gallery screen with Images, Documents, Videos tabs with upload feature |  | Close
161 | Manage Data > Traffic Volume Counts | upload the images, documents from the respective tabs |  | Close
162 | Manage Data > Traffic Volume Counts | displays the uploaded images and documents in the respective tabs |  | Close
163 | Manage Data > Traffic Volume Counts | Videos can be viewed, if any added from the backend at the respective path (Application folder/WebAPI/Gallery/Videos) | bhanu please update on this task as you have made few changes in this
164 | Manage Data > Traffic Volume Counts | when click on back (<<) icon show the table screen back |  | Close
165 | Manage Data > Traffic Volume Counts | Export the table data in excel (.csv) format | if possible, try to set the file name as the menu name | Close
166 | Manage Data > Traffic Distribution | Show column headers of the respective table | columns not loading when the page is loaded for the first time | Open
167 | Manage Data > Traffic Distribution | Show the data in table based on the filter selection |  | Close
168 | Manage Data > Traffic Distribution | Links dropdown should fill based on the road selected |  | Close
169 | Manage Data > Traffic Distribution | Clear the filter and show complete data in table, when click on clear filters icon |  | Close
170 | Manage Data > Traffic Distribution | Action icons order Add ; Edit ; Delete ; Export |  | Close
171 | Manage Data > Traffic Distribution | Show the add new traffic volume count data screen when click on Add New icon |  | Close
172 | Manage Data > Traffic Distribution | show the data of the selected item in form layout when click on Edit icon | 1. Buttons not aligned properly 2. check the UI, maybe the road field can be kept in top row like survey year can be made col2, then road col4 and link also col4 in top row, then 2nd row traffic station col3, weightage col2, surveydate col2, remarks col5, then 3rd row right aligned buttons. 3. weightage value - validate as 0 - 100 with decimals | Open
173 | Manage Data > Traffic Distribution | Show red * mark for mandatory fields |  | Close
174 | Manage Data > Traffic Distribution | Cancel the add/edit screen and go back to table layout when click on cancel button in add/edit screen |  | Close
175 | Manage Data > Traffic Distribution | Add / update the new entered data and go back to table screen and refresh the table when submit button is clicked |  | Close
176 | Manage Data > Traffic Distribution | Delete the selected item when clicked on delete icon |  | Close
177 | Manage Data > Traffic Distribution | Export the table data in excel (.csv) format | if possible, try to set the file name as the menu name | Close
178 | Manage Data > Axle Load Survey | Show column headers of the respective table | columns not loading when the page is loaded for the first time | Open
179 | Manage Data > Axle Load Survey | Show the data in table based on the filter selection |  | Close
180 | Manage Data > Axle Load Survey | Links dropdown should fill based on the road selected |  | Close
181 | Manage Data > Axle Load Survey | Clear the filter and show complete data in table, when click on clear filters icon |  | Close
182 | Manage Data > Axle Load Survey | Action icons order Add ; Edit ; Delete ; Export |  | Close
183 | Manage Data > Axle Load Survey | Show the add new traffic volume count data screen when click on Add New icon |  | Close
184 | Manage Data > Axle Load Survey | show the data of the selected item in form layout when click on Edit icon | 1. Buttons not aligned properly 2. Vehicle Type dropdown is now changed to Vehicle name textbox, so remove the dropdown and change it to vehicle name and it is not mandatory, need not check for validation. 3. axle7 field is not added. 4. arrange the mandatory fields first then the other fields | Open
185 | Manage Data > Axle Load Survey | Show red * mark for mandatory fields | remove red * mark for Vehicle Type (now changed to Vehicle Name) field | Open
186 | Manage Data > Axle Load Survey | Cancel the add/edit screen and go back to table layout when click on cancel button in add/edit screen |  | Close
187 | Manage Data > Axle Load Survey | Add / update the new entered data and go back to table screen and refresh the table when submit button is clicked | showing error since new changes to be done | Open
188 | Manage Data > Axle Load Survey | Delete the selected item when clicked on delete icon | need to check the delete once, looks like more than 1 row is getting deleted | Open
189 | Manage Data > Axle Load Survey | Export the table data in excel (.csv) format | if possible, try to set the file name as the menu name | Close
190 | Execute Process > Check Missing Data | Survey year to be binded by default with the first value in the dropdown |  | Close
191 | Execute Process > Check Missing Data | below tables to be shown in the table dropdown Axle Load Survey, Traffic Distribution, Traffic Stations, Traffic Volume Counts |  | Close
192 | Execute Process > Check Missing Data | when we click on the respective row in the summary table where the status is failed and error count is > 0 then the error log screen is opened |  | Close
193 | Execute Process > Check Missing Data | Error log should be exportable and show selected process summary | 1. Show the selected process summary in this screen. 2. Add an export icon to export the error log. | New
194 | Execute Process > Check Missing Data | when we click on the back(<<) button in error log screen it shows the table back |  | Close
195 | Execute Process > Check Missing Data | when we click on the respective row in the summary table open the missing data table (oMissingData) screen | 1. Show the selected process summary in this screen. 2. as of now we need to navigate to reports > Processed data > Missing Data menu link. 3. should have a back (<<) button which will show the summary table | New
196 | Execute Process > Data Aggregation | Survey year to be binded by default with the first value in the dropdown |  | Close
197 | Execute Process > Data Aggregation | below tables to be shown in the table dropdown Axle Load Survey, Traffic Distribution, Traffic Stations, Traffic Volume Counts |  | Close
198 | Execute Process > Data Aggregation | when we click on the respective row in the summary table where the status is failed and error count is > 0 then the error log screen is opened |  | Close
199 | Execute Process > Data Aggregation | Error log should be exportable and show selected process summary | 1. Show the selected process summary in this screen. 2. Add an export icon to export the error log. | New
200 | Execute Process > Data Aggregation | when we click on the back(<<) button in error log screen it shows the table back |  | Close
201 | Execute Process > Set GPS Coordinates | Survey year to be binded by default with the first value in the dropdown |  | Close
202 | Execute Process > Set GPS Coordinates | below tables to be shown in the table dropdown Axle Load Survey, Traffic Distribution, Traffic Stations, Traffic Volume Counts |  | Close
203 | Execute Process > Set GPS Coordinates | all the roads based on the user access should be shown in the road dropdown | Road dropdown is missing the label | Open
204 | Execute Process > Set GPS Coordinates | when we click on the respective row in the summary table where the status is failed and error count is > 0 then the error log screen is opened |  | Close
205 | Execute Process > Set GPS Coordinates | Error log should be exportable and show selected process summary | 1. Show the selected process summary in this screen. 2. Add an export icon to export the error log. | New
206 | Execute Process > Set GPS Coordinates | when we click on the back(<<) button in error log screen it shows the table back |  | Close
207 | Execute Process > Generate ADT and AADT | Survey year to be binded by default with the first value in the dropdown | 1. Merge the existing 3 processes Prepare ADT day-wise; prepare avg.ADT day-wise; generate ADT station-wise. 2. combine the descriptions of the 3 processes as well. | New
208 | Execute Process > Generate ADT and AADT | when we click on the respective row in the summary table where the status is failed and error count is > 0 then the error log screen is opened |  | New
209 | Execute Process > Generate ADT and AADT | Error log should be exportable and show selected process summary | 1. Show the selected process summary in this screen. 2. Add an export icon to export the error log. | New
210 | Execute Process > Generate ADT and AADT | when we click on the back(<<) button in error log screen it shows the table back |  | New
211 | Execute Process > Generate ADT and AADT | when we click on the row in the table where status is success, then open the ADT station-wise output table | 1. Show the selected process summary in this screen. 2. Add an export icon to export the error log. 3. Add a back (<<) button, which when clicked show the process screen | New
212 | Execute Process > Queuing Length | Show the quequing form |  | Close
213 | Execute Process > Queuing Length | allow the user to enter the input fields |  | Close
214 | Execute Process > Queuing Length | calculate and show the final output based on the inputs given | a few items need clarification as per surender | Close
215 | Execute Process > Queuing Length | print the form in pdf when click on print button |  | Close
216 | Execute Process > Queuing Length | clear the form inputs to default when click on clear button |  | Close
217 | Execute Process > Generate VDF | Survey year to be binded by default with the first value in the dropdown | change the menu as generate VDF instead of generate VDF and road life | Close
218 | Execute Process > Generate VDF | when we click on the respective row in the summary table where the status is failed and error count is > 0 then the error log screen is opened |  | Close
219 | Execute Process > Generate VDF | Error log should be exportable and show selected process summary | 1. Show the selected process summary in this screen. 2. Add an export icon to export the error log. | New
220 | Execute Process > Generate VDF | when we click on the back(<<) button in error log screen it shows the table back |  | Close
221 | Execute Process > Generate VDF | when we click on the row in the table where status is success, then open the VDF output table | 1. Show the selected process summary in this screen. 2. Add an export icon to export the error log. 3. Add a back (<<) button, which when clicked show the process screen | New
222 | Execute Process > Generate Traffic Projection | Survey year to be binded by default with the first value in the dropdown |  | Close
223 | Execute Process > Generate Traffic Projection | when we click on the respective row in the summary table where the status is failed and error count is > 0 then the error log screen is opened |  | Close
224 | Execute Process > Generate Traffic Projection | Error log should be exportable and show selected process summary | 1. Show the selected process summary in this screen. 2. Add an export icon to export the error log. | New
225 | Execute Process > Generate Traffic Projection | when we click on the back(<<) button in error log screen it shows the table back |  | Close
226 | Execute Process > Generate Traffic Projection | when we click on the row in the table where status is success, then open the Traffic Projection output table | 1. Show the selected process summary in this screen. 2. Add an export icon to export the error log. 3. Add a back (<<) button, which when clicked show the process screen | New
227 | Execute Process > Generate Traffic Growth Rate | Survey year to be binded by default with the first value in the dropdown |  | Close
228 | Execute Process > Generate Traffic Growth Rate | when we click on the respective row in the summary table where the status is failed and error count is > 0 then the error log screen is opened |  | Close
229 | Execute Process > Generate Traffic Growth Rate | Error log should be exportable and show selected process summary | 1. Show the selected process summary in this screen. 2. Add an export icon to export the error log. | New
230 | Execute Process > Generate Traffic Growth Rate | when we click on the back(<<) button in error log screen it shows the table back |  | Close
231 | Execute Process > Generate Traffic Growth Rate | when we click on the row in the table where status is success, then open the Traffic Growth Rate output table | 1. Show the selected process summary in this screen. 2. Add an export icon to export the error log. 3. Add a back (<<) button, which when clicked show the process screen | New
232 | Reports > Processed Data > Missing Data |  | remove this menu item since this output is being shown as part of the execute process screen | New
233 | Reports > Daily Count Direciton-wise | Survey year to be binded by default with the first value in the dropdown |  | Close
234 | Reports > Daily Count Direciton-wise | Province, district, roads, stations dropdowns to be dependent in the same order | sub-filters dropdown values not getting cleared based on the selection of parent filter dropdown | Open
235 | Reports > Daily Count Direciton-wise | clear the filters to default when clicked on clear filters button |  | Close
236 | Reports > Daily Count Direciton-wise | generate report based on the filter selected | 1. change the report headers - Class-1 as Motor Cycle ; class-2 as Light Vehicles ; class-3 as Heavy Vehicles 2. ideally, 5 days it is 12 hrs, and 2 days it is 24 hrs, so night rows should be 2 instead of 4 (I have made these changes in SP) | Open
237 | Reports > Daily Count Direciton-wise | print the report in word, excel, pdf formats |  | Close
238 | Reports > Daily Count Direciton-wise | pagination in the report and also refresh data |  | Close
239 | Reports > Daily Count Direciton-wise | we need a dropdown for report type - Road wise or District-wise | based on the selection the report format will change as below if District-wise then report will be as existing and if road-wise then show in one single page order by total ADT and direction in descending order. 2. by default road-wise report type to be shown | New
240 | Reports > Daily Traffic Count | Survey year to be binded by default with the first value in the dropdown |  | Close
241 | Reports > Daily Traffic Count | Province, district, roads, stations dropdowns to be dependent in the same order | sub-filters dropdown values not getting cleared based on the selection of parent filter dropdown | Open
242 | Reports > Daily Traffic Count | clear the filters to default when clicked on clear filters button |  | Close
243 | Reports > Daily Traffic Count | generate report based on the filter selected | ideally, 5 days it is 12 hrs, and 2 days it is 24 hrs, so night rows should be 2 instead of 4 (I have made these changes in SP) | Open
244 | Reports > Daily Traffic Count | print the report in word, excel, pdf formats |  | Close
245 | Reports > Daily Traffic Count | pagination in the report and also refresh data |  | Close
246 | Reports > Daily Traffic Count | we need a dropdown for report type - Road wise or District-wise | based on the selection the report format will change as below if District-wise then report will be as existing and if road-wise then show in one single page order by total ADT descending | New
247 | Reports > Average Daily Traffic (ADT) | Survey year to be binded by default with the first value in the dropdown |  | Close
248 | Reports > Average Daily Traffic (ADT) | Province, district, roads, stations dropdowns to be dependent in the same order | sub-filters dropdown values not getting cleared based on the selection of parent filter dropdown | Open
249 | Reports > Average Daily Traffic (ADT) | clear the filters to default when clicked on clear filters button |  | Close
250 | Reports > Average Daily Traffic (ADT) | generate report based on the filter selected | 1. Add Annual Average Daily Traffic before the Directional Split row in the report. 2. check the values of day 3 and day 6 based on the excel reference. 3. Add V/C ratio row after the AADT (point 1 row). 4. Also add PCU values row after V/C ratio (point 3 row). 5. Change Factor for 24 hours as "K-Factor for 24 hours" 6. Change Day Traffic of Maximum as "Peak-hour data for 24 hours" 7. Change the existing label "Total AADT as Total ADT". 8. Add new column "Total AADT" after "Total ADT" column. 9. Add seasonal factors column in the top details bar. If no value then default is 1. | Open
251 | Reports > Average Daily Traffic (ADT) | print the report in word, excel, pdf formats |  | Close
252 | Reports > Average Daily Traffic (ADT) | pagination in the report and also refresh data |  | Close
253 | Reports > Daily ADT Distribution | Survey year to be binded by default with the first value in the dropdown |  | Close
254 | Reports > Daily ADT Distribution | Province, district, roads, stations dropdowns to be dependent in the same order | sub-filters dropdown values not getting cleared based on the selection of parent filter dropdown | Open
255 | Reports > Daily ADT Distribution | clear the filters to default when clicked on clear filters button |  | Close
256 | Reports > Daily ADT Distribution | generate report based on the filter selected | 1. change the report headers - Class-1 as Motor Cycle ; class-2 as Light Vehicles ; class-3 as Heavy Vehicles. 2. Add seasonal factors column in the top details bar. If no value then default is 1. 3. Add Average AADT row after the Average ADT row. | Open
257 | Reports > Daily ADT Distribution | print the report in word, excel, pdf formats |  | Close
258 | Reports > Daily ADT Distribution | pagination in the report and also refresh data |  | Close
259 | Reports > Daily ADT Distribution | two charts per station are also to be shown for this report |  | Close
260 | Reports > ADT Distribution by Mode | Survey year to be binded by default with the first value in the dropdown |  | Close
261 | Reports > ADT Distribution by Mode | Province, district, roads, stations dropdowns to be dependent in the same order | sub-filters dropdown values not getting cleared based on the selection of parent filter dropdown | Open
262 | Reports > ADT Distribution by Mode | clear the filters to default when clicked on clear filters button |  | Close
263 | Reports > ADT Distribution by Mode | generate report based on the filter selected | 1. Data not showing, check the report output 2. Add AADT column after ADT in the report. 3. Add seasonal factor value in the top row | Open
264 | Reports > ADT Distribution by Mode | print the report in word, excel, pdf formats |  | Close
265 | Reports > ADT Distribution by Mode | pagination in the report and also refresh data |  | Close
266 | Reports > ADT Distribution by Mode | one chart per station are also to be shown for this report |  | Close
267 | Reports > ADT Hourly Variation | Survey year to be binded by default with the first value in the dropdown |  | Close
268 | Reports > ADT Hourly Variation | Province, district, roads, stations dropdowns to be dependent in the same order | sub-filters dropdown values not getting cleared based on the selection of parent filter dropdown | Open
269 | Reports > ADT Hourly Variation | clear the filters to default when clicked on clear filters button |  | Close
270 | Reports > ADT Hourly Variation | generate report based on the filter selected | Giving error, data not showing, check the report output | Open
271 | Reports > ADT Hourly Variation | print the report in word, excel, pdf formats |  | Close
272 | Reports > ADT Hourly Variation | pagination in the report and also refresh data |  | Close
273 | Reports > ADT Hourly Variation | one chart per station are also to be shown for this report |  | Close
274 | Reports > ADT by Station | Survey year to be binded by default with the first value in the dropdown |  | Close
275 | Reports > ADT by Station | Province, district, roads, stations dropdowns to be dependent in the same order | sub-filters dropdown values not getting cleared based on the selection of parent filter dropdown | Open
276 | Reports > ADT by Station | Threshold minimum and maximum ADT textbox for filter |  | Close
277 | Reports > ADT by Station | based on the selection the report format will change as below if District-wise then report will be as existing and if road-wise then show in one single page order by total ADT descending |  | Close
278 | Reports > ADT by Station | clear the filters to default when clicked on clear filters button |  | Close
279 | Reports > ADT by Station | generate report based on the filter selected | 1. Add Total AADT column at the last in the report. 2. add seasonal factor values in the top row | Open
280 | Reports > ADT by Station | print the report in word, excel, pdf formats |  | Close
281 | Reports > ADT by Station | pagination in the report and also refresh data |  | Close
282 | Reports > Vehicle Damage Factor (VDF) | Survey year to be binded by default with the first value in the dropdown |  | Close
283 | Reports > Vehicle Damage Factor (VDF) | Province, district, roads, stations dropdowns to be dependent in the same order | sub-filters dropdown values not getting cleared based on the selection of parent filter dropdown | Open
284 | Reports > Vehicle Damage Factor (VDF) | based on the selection the report format will change as below if District-wise then report will be as existing and if road-wise then show in one single page order by total ADT descending |  | Close
285 | Reports > Vehicle Damage Factor (VDF) | clear the filters to default when clicked on clear filters button |  | Close
286 | Reports > Vehicle Damage Factor (VDF) | generate report based on the filter selected | Giving error, data not showing, check the report output | Open
287 | Reports > Vehicle Damage Factor (VDF) | print the report in word, excel, pdf formats |  | Close
288 | Reports > Vehicle Damage Factor (VDF) | pagination in the report and also refresh data |  | Close
289 | Reports > Traffic Growth Rate | Survey year to be binded by default with the first value in the dropdown |  | Close
290 | Reports > Traffic Growth Rate | Province, district, roads, stations dropdowns to be dependent in the same order | sub-filters dropdown values not getting cleared based on the selection of parent filter dropdown | Open
291 | Reports > Traffic Growth Rate | we need a dropdown for report type - Road wise or District-wise | based on the selection the report format will change as below if District-wise then report will be as existing and if road-wise then show in one single page order by total ADT descending | Open
292 | Reports > Traffic Growth Rate | clear the filters to default when clicked on clear filters button |  | Close
293 | Reports > Traffic Growth Rate | generate report based on the filter selected |  | Close
294 | Reports > Traffic Growth Rate | print the report in word, excel, pdf formats |  | Close
295 | Reports > Traffic Growth Rate | pagination in the report and also refresh data |  | Close
296 | Reports > Traffic Projection | Survey year to be binded by default with the first value in the dropdown |  | Close
297 | Reports > Traffic Projection | Province, district, roads, stations dropdowns to be dependent in the same order | sub-filters dropdown values not getting cleared based on the selection of parent filter dropdown | Open
298 | Reports > Traffic Projection | we need a dropdown for report type - Road wise or District-wise | based on the selection the report format will change as below if District-wise then report will be as existing and if road-wise then show in one single page order by total ADT descending | Open
299 | Reports > Traffic Projection | clear the filters to default when clicked on clear filters button |  | Close
300 | Reports > Traffic Projection | generate report based on the filter selected | data not showing, check the report output | Open
301 | Reports > Traffic Projection | print the report in word, excel, pdf formats |  | Close
302 | Reports > Traffic Projection | pagination in the report and also refresh data |  | Close

## RLRS
S.No. | Menu / Page | Item Description | Remarks | DEV | QA | STAGE
| Network Management > Network Data > Impassable Data |  |  | New
| Network Management > Network Data > Overlap Data |  |  | New